## Sept 2015
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS OR ACTIVITIES
FOR THE MONTH SEPTEMBER 30, 2015
TRUST FUND
Province, City or Municipality: TAGUM CITY
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
CONSTRUCTION IN PROGRESS (CIP) PROJECTS
DPWH SLRF - ADDITIONAL LAYER OF ASPHALT NECESSARY TO COVER IMPERFECTIONS AND SCALPING OF EXISTING CONCRETE | Brgy. San Miguel | 695223.91 | 2014-11-16 | 2015-03-04 | 100% | 593951.6 |  | COMPLETED | **
DPWH SLRF - DRAINAGE IMPROVEMENT AT TIMOG ROAD, BRGY. VISAYAN VILLAGE, T.C. | Brgy. Visayan Village | 919461.75 | 2014-11-16 | 2015-05-08 | 100% | 912747.92 |  | COMPLETED | *
DPWH SLRF- TAGUM CITY LOCAL ROAD MAINT. 2013, BRGY. POBLACION, TC | Brgy. Poblacion | 2873219.52 | 2015-03-31 | 2015-05-29 | 100% | 2866075 |  | COMPLETED | **
DPWH SLRF - TAGUM CITY LOCAL ROAD MAINT. 2013, VILLA PARAISO, BRGY. | Brgy. Visayan Village | 1444455.34 | 2015-01-12 | 2015-02-11 | 100% | 1433658.73 |  | COMPLETED | **
NMIS - CONSTRUCTION OF TAGUM CITY'S NEW "AA" SLAUGHTERHOUSE | Brgy. Magdum | 10000000 | 2014-05-01 | 2015-05-29 | 100% | 8295079.95 |  | COMPLETED | **
DA BFAR - PROPOSED CONSTRUCTION OF MULTI SPECIES ALGAL TANK, PLUMBING & ELECTRICAL - BRGY. LIBOGANON, TAGUM CITY | Brgy. Liboganon | 480000 | 2014-11-17 | 2015-05-15 | 100% | 485330.11 |  | COMPLETED | * | -5330.11
DA BFAR - PROPOSED CONSTRUCTION OF SALINE TILAPIA HATCHERY - BRGY. BINCUNGAN, TAGUM CITY | Brgy. Bincungan | 170000 | 2014-12-08 | 2015-04-01 | 100% | 165129.81 |  | COMPLETED | *
DA BFAR - PROPOSED CONSTRUCTION OF MULTI SPECIES (RESERVOIR/WATER TANK) - BRGY. LIBOGANON, TAGUM CITY | Brgy. Liboganon | 200000 | 2014-04-10 | 2015-05-15 | 100% | 211049 |  | COMPLETED | *
DA BFAR - PROPOSED CONSTRUCTION OF MULTI SPECIES (LARVAL BUILDING) - BRGY. LIBOGANON, TAGUM CITY | Brgy. Liboganon | 1550000 | 2014-04-07 | 2015-05-15 | 100% | 1598583.61 |  | COMPLETED | *
DA- DIDP CONCRETING OF PRK. 1 TO PRK 2, BRGY. LIBOGANON, TAGUM CITY | Brgy. Liboganon | 2910000 | 2015-01-05 | 2015-08-07 | 100% | 2778101.96 |  | COMPLETED | *
DEP ED-FABRICATION OF SCHOOL FURNITURES 2014 B | Brgy. East | 900000 |  |  | 100% | 893926 |  | COMPLETED
DEP ED- DEVELOPMENT OF SCHOOL FURNITURES 2014 | Brgy. East | 1000000 |  |  | 100% | 943915.5 |  | COMPLETED
DEP ED - FABRICATION OF SCHOOL FURNITURES 2014 A | Brgy. East | 1000000 |  |  | 100% | 978422.5 |  | COMPLETED
ECCDC - INST. OF SECURITY GRILLS FOR WINDOWS & OTHERS ADD'LL ITEMS | Various Barangay | 27049.66 |  |  | 100% | 19125 |  | COMPLETED
DILG - CONST'N/COMPLETION OF MULTI-PURPOSE BLDG, PASALUBONG CENTER | Brgy. Apokon | 3000000 | [5 empty] | NO DISBURSEMENTS YET
DILG - LOCAL ACCESS ROAD PROJECT UNDER INFRE INVESTMENT | Various Barangay | 5760000 | [5 empty] | NO DISBURSEMENTS YET
DEPED - DEVELOPMENT OF SCHOOL FURNITURES | Various Barangay | 1722037.4 | [5 empty] | NO DISBURSEMENTS YET
NON-CIP PROJECTS/PROGRAMS
DENR - BARANGAY FOREST PROGRAM AT BRGY. BINCUNGAN AND CANOCOTAN | Brgy. Bincungan | 175000 | [5 empty] | NO DISBURSEMENTS YET | **
DENR - NATIONAL GREENING PROGRAM | Various Barangay | 495000 |  |  |  | 156295 |  | ON GOING | **
DA BFAR - MANGROVE ENHANCEMENT PROJECT (60,000 UNITS MANGROVE) | Brgy. Liboganon, Bincungan | 360000 |  |  |  | 193720 |  | ON GOING | **
DOLE - LIVELIHOOD ASSISTANCE | Various Barangay | 9896100 |  |  |  | 9896100 |  | NO DISBURSEMENTS YET | **
DA -RFUXI ESTABLISHMENT OF EMRC PRODUCTION FARM | Various Barangay | 1822500 |  |  |  | 1813994 |  | ON GOING | **
DA - NATIVE CHICKEN AND GOAT PRODUCTION | Various Barangay | 112000 |  |  |  | 111100 |  | ON GOING | **
DA - INPUTS AND COMPENSATION OF MINI RICE MILL | Brgy. Pagsabangan | 1000000 |  |  |  | 122624 |  | ON GOING | **
DA - ANIMAL NATIVE HOG PRODUCTION | Brgy. La Filipina | 100000 |  |  |  | 36144 |  | ON GOING | **
DA - ANIMAL NATIVE POULTRY PRODUCTION | Brgy. Nueva Fuerza | 80000 |  |  |  | 43819 |  | ON GOING | **
DA - TRAINING FACILITIES FOR AGRI CULTURE PROJECT | Various Barangay | 350000 | [5 empty] | NO DISBURSEMENTS YET | **
DA - PROMTION & DEV'T OF MINI FEEDMILL | Brgy. La Filipina | 160000 | [5 empty] | NO DISBURSEMENTS YET | **
DA - PROCUREMENT OF ONE UNIT MOBILE VERTICAL GRAIN DRYER | Various Barangay | 3500000 | [5 empty] | NO DISBURSEMENTS YET | **
DA- NATIONAL FISHERIES PROGRAM-BUNSOD/BENTOL FISHING CAGE | Brgy. Liboganon | 208000 |  |  |  | 590 |  | ON GOING | **
DA- NATIONAL HIGH VALUE CROP PROGRAM-COCONUT FARM DEVELOPMENT & REHABILITATION | Various Barangay | 640000 | [5 empty] | NO DISBURSEMENTS YET | **
DA- PROMOTION & DEVELOPMENT OF URBAN FARMING-CONTAINER GARDENING | Brgy. Liboganon, Lower Busaon | 160000 |  |  |  | 143879 |  | ON GOING | **
DA- PROMOTION & DEVELOPMENT OF ORGANIC - VERMICAST PRODUCTION | San Agustin | 160000 |  |  |  | 43198 |  | ON GOING | **
DOH - PERFORMANCE INCENTIVES-MUNICIPAL LEADERSHIP AND GOVERNANCE | Various Barangay | 250000 | [5 empty] | NO DISBURSEMENTS YET | **
DOH - REPAIR AND RENOVATION OF RHU FOR TB DOTS SERVICES | Various Barangay | 40100.4 | [5 empty] | NO DISBURSEMENTS YET | **
DOH - PHILHEALTH FOR TAGUM PPM DOTS CENTER | Various Barangay | 474632.88 |  |  |  | 469165.88 |  | ON GOING | **
DEPED - REPAIR AND MAINTENANCE OF SCHOOL BUILDING ( 2015 PALARONG PAMBANSA) | Various Barangay | 4500000 |  |  |  | 3967123.49 |  | ON GOING | **
DSWD - SUPPLEMENTARY FEEDING PROGRAM FOR CHILDREN ENROLLED IN DAY CARE CENTERS | Various Barangay | 6784488.8 |  |  |  | 6784488.8 |  | NO DISBURSEMENTS YET | **
DSWD - SOCIAL PENSION FOR INDIGENT SENIOR CITIZEN | Various Barangay | 1954500 |  |  |  | 1912500 |  | ON GOING | **
DSWD - CORE SHELTER PROGRAM | Various Barangay | 4630000 |  |  |  | 4630000 |  | NO DISBURSEMENTS YET | **
HUDC - BEST PRACTICES AWARD FOR DRIVE AGAINTS PROFESSIONAL SQUATERS | Various Barangay | 130000 |  |  |  | 127987 |  | ON GOING | **
DTI PRODUCTIVITY ENHANCEMENT & ENTERPRENUERIAL DEVELOPMENT | Various Barangay | 960000 | [5 empty] | NO DISBURSEMENTS YET | **
DTI - BALAY SANG PAMILIHAN | Various Barangay | 500000 | [5 empty] | NO DISBURSEMENTS YET | **
DTI - CAPACITY BUILDING | Various Barangay | 500000 | [5 empty] | NO DISBURSEMENTS YET | **
DTI - YAMAN PINOY | Various Barangay | 500000 | [5 empty] | NO DISBURSEMENTS YET | **
PHILHEALTH CAPITATION FUND | Various Barangay | 2887712.54 |  |  |  | 2321742.69 |  | ON GOING
PHILHEALTH CAPITATION FUND 4TH QTR. OF 2013 | Various Barangay | 465500 |  |  |  | 252195 |  | ON GOING | **
PHILHEALTH PRIMARY CARE BENEFIT -1ST & 2ND QTR. OF 2014 | Various Barangay | 1885775 |  |  |  | 594549.18 |  | ON GOING | **
PHILHEALTH PRIMARY CARE BENEFIT - 3RD QTR. OF 2014 | Various Barangay | 1342275 |  |  |  | 436294.7 |  | ON GOING | **
We hereby certify that we have reviewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
document.
Prepared by: |  | Noted by: |  |  |  | ALLAN L. RELLON, DPA, Ph.D
KENT R. DUQUE |  |  | RAMIL Y. TIU, CPA
Mgt. & Audit Analyst |  |  | CITY ACCOUNTANT |  |  | LOCAL CHIEF EXECUTIVE