## MOOE
Republic of the Philippines
Province of Davao del Norte
City of Tagum
OFFICE OF THE CITY BUDGET OFFICER
PROJECT MONITORING REPORT
MAINTENANCE & OTHER OPERATING EXPENSES (MOOE)
For the 3rd Quarter, CY 2015
Ref No. | Particulars | Location | Total Cost | Date Started | Target Completion Date | % of Completion | Total Cost Incurred to Date | No. of Extensions, if any | Remarks
003-01-15 | Repairs & maintenance- Park and Plaza |  | 355000 |  |  |  | 208132.66
004-01-15 | Repairs & maintenance of Structures @ Tagum City | Tagum | 1000000 |  |  |  | 855554.63
006-01-15 | Repairs & maintenance- City Gov't Bldg & Demolition |  | 2595000 |  |  |  | 2125238.1
005-01-15 | Fab. Of RCPC, CHB & Paving blocks |  | 2110000 |  |  |  | 1379449.33
008-05-14 | Repair and Maintenance of Water Treatment @ Motorpool Compound | Magugpo East | 150000 | 2014-01-06 | 2015-02-28 | 100% |  |  | Completed per POW
010-01-15 | Repairs & maintenance- Airconditioning facilities |  | 300000 |  |  |  | 177598
013-01-15 | Repairs & maintenance- Asphalt Plant |  | 500000 |  |  |  | 423440
017-01-15 | Repairs & maintenance- Park and Plaza |  | 300000 |  |  |  | 281571
033-01-15 | Repairs & maintenance of roads @ Tagum City | Tagum | 1000000 |  |  |  | 776891.82
084-03-15 | Repair and Maintenance of Playing Venues @ San Miguel Gym | San Miguel | 122000 | 2015-04-01 | 2015-06-30 | 100% |  |  | Completed
085-03-15 | Repair and Maintenance of Playing Venues @ Max Mirafuentes Academy | Magugpo North | 7000 | 2015-04-01 | 2015-06-30 | 100% |  |  | Completed
086-03-15 | Repair and Maintenance of Playing Venues @ Mankilam Gym | Mankilam | 78000 | 2015-04-01 | 2015-06-30 | 100% |  |  | Completed
087-03-15 | Repair and Maintenance of Playing Venues @ Apokon Gym | Apokon | 215000 | 2015-04-01 | 2015-06-30 | 100% |  |  | Completed
088-03-15 | Repair and Maintenance of Playing Venues @ USEP Gym | Apokon | 215000 | 2015-04-01 | 2015-06-30 | 100% |  |  | Completed
089-03-15 | Repair and Maintenance of Playing Venues @ Magugpo North Gym | Magugpo North | 53000 | 2015-04-01 | 2015-06-30 | 100% |  |  | Completed
090-03-15 | Repair and Maintenance of Playing Venues @ E-PARK | Apokon | 730000 | 4//1/15 | 2015-06-30 | 100% |  |  | Completed
091-03-15 | Repair and Maintenance of Playing Venues @ Rotary Park | Magugpo Poblacion | 280000 | 2015-04-01 | 2015-06-30 | 100% |  |  | Completed
143-03-15 | Repairs & maintenance- City Gov't Bldgs @ Fireworks Canocotan | Canocotan | 15513 |  |  |  | 15513 |  | Completed
144-03-15 | Repairs & maintenance- Tagum Overland Transport Integrated Terminal |  | 21107 |  |  |  | 20100 |  | Completed
148-03-15 | Repairs & maintenance- New Tagum Public Market | Magugpo West | 65000 |  |  |  | 65000 |  | Completed
182-04-15 | Asphalting of Roads @ USEP Tagum Compound | Apokon | 2005099 | 2015-05-01 |  | 28% | 1384150.03 |  | On- going
183-04-15 | Asphalting of Roads @ USEP Mampesing Compound | Comval Province | 1494901 | 2015-06-01 |  | 10% | 1036302.46 |  | On- going
230-05-15 | Asphalt Overlay | Panabo City | 2207282.55 | 2015-06-01 |  | 95% | 1742100.85 |  | Physically Completed
253-06-15 | Asphalting Roads @ Secdea Beach Resort Compound, San Isidro, Babak | IGACOS | 3018923 | 2015-06-16 |  | 40% | 2389190.45 |  | On- going
263-06-15 | Repair/ Maintenance of Roads @ Various Location w/n Tagum City | Tagum | 450000 |  |  |  | 46827.7
307-08-15 | Repair & Maintenance- City Gov't Buildings | Tagum | 210000 | [5 empty] | POW Approved
285-07-15 | Sales of Hotmix Asphalt @ Various Clienteles ( 2 Degrees, DPWH, Tagum Builders, LLM Concrete Products, & Comval Views | Various | 2578215 |  |  |  | 1884319.37
286-07-15 | Asphalt Overlay @ SECDEA Beach Resort Compound Phase II, San Isidro, Babak | Island Garden City | 15183442 |  |  |  | 11723772.36
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
Prepared by: |  |  |  |  | Attested by:
| NORHANIAH S. DISOMA, CPA |  |  |  |  | RODILIO S. DINOPOL, CE
| Clerk I |  |  |  |  | Project Monitoring In- Charge
Noted by: |  |  |  |  | Approved by:
| ARCADIA E. YLANAN, CPA, MBA |  |  |  |  | ALLAN L. RELLON, DPA, Ph.D.
| City Budget Officer |  |  |  |  | City Mayor

## Sheet1
FDP For 7 - Capital Outlay
Republic of the Philippines
Province of Davao del Norte
City of Tagum
OFFICE OF THE CITY BUDGET OFFICER
PROJECT MONITORING REPORT
CAPITAL OUTLAY
For the 3rd Quarter, CY 2015
Province, City or Municipality: TAGUM CITY
Ref No. | Particulars | Location | Total Cost | Date Started | Target Completion Date | % of Completion | Total Cost Incurred to Date | No. of Extensions, if any | Remarks
016-01-14 | Completion of two- storey school building @ Tagum City Trade School | Apokon | 500000 | 2014-03-01 | 2015-05-31 | 100% |  |  | Completed
017-01-14 | Construction of Comfort Room at New 2- Storey School Building Tagum City Trade School | Apokon | 300000 | 2014-03-01 | 2015-06-15 | 100% |  |  | Completed
028-02-14 | School Fencing at Bincungan Elem. School | Bincungan | 170000 | 2014-02-17 | 2015-01-17 | 100% |  |  | Completed per POW
029-02-14 | School Fencing at Madaum Elem. School | Madaum | 330000 | 2014-02-17 | 2015-01-15 | 100% |  |  | Completed per POW
102-04-14 | Rehabilitation/ Construction of Drainage @ Prk. 6, Agan | Magdum | 500000 | 2015-03-09 | 2015-05-15 | 100% |  |  | Completed per POW
114-05-14 | Rehabilitation/ Construction of Drainage (w/out cover) @ Purok 6, Agan | Magdum | 500000 | 2015-03-09 | 2015-05-15 | 100% |  |  | Completed per POW
123-05-14 | Construction of Meat Processing Area @ New Public Market | M. West | 1000000 | 2014-08-01 |  | 70.32% |  |  | Suspended- Waiting for Addt'l Mat
126-05-14 | Construction of Bridges (Construction of Flat Slab & Pathways) | Nueva Fuerza | 500000 | 2014-09-01 | 2015-07-31 | 100% |  |  | Completed per POW
127-05-14 | Construction/ Completion of Multi-purpose Buliding Construction of Sanitation Vehicle Garage Phase 1 @ Motorpool Compound | Magugpo East | 800000 | 2014-07-25 | 2015-02-15 | 100% |  |  | Completed per POW
133-03-15 | Rehabilitation/ Covering of Drainage (Top Slab) @ Mangga Elementary School | Visayan Village | 300000 |  |  |  | 245101
139-06-14 | Rehabilitation/ Construction of Drainage @ Iga-uy, Durian Avenue | Madaum | 1000000 | 2015-09-09 | 2015-02-10 | 100% |  |  | Completed per POW
143-06-14 | Construction of 6 Temporary Classroom @ Tagum City Trade School | Apokon | 700000 | 2014-07-16 | 2015-02-10 | 100% |  |  | Completed per POW
178-07-14 | Rehabilitation/ Construction of Drainage @ Suaybaguio District | Magugpo North | 175000 | 2014-07-15 | 2015-01-31 | 100% |  |  | Completed per POW
179-07-14 | Construction of School Building Magugpo Pilot Central Elem. School | Magugpo South | 1730000 | 2014-08-16 | 2015-02-28 | 100% |  |  | Completed per POW
187-07-14 | Rehabilitation/ Construction of Drainage @ Prk. Cabadiangan | San Isidro | 450000 | 2014-10-10 | 2015-02-15 | 100% |  |  | Completed per POW
189-07-14 | Rehabilitation/ Construction of Drainage @ Prk. Santol | La Filipina | 500000 | 2014-11-01 | 2015-02-15 | 100% |  |  | Completed per POW
216-09-14 | Concreting of Roads @ Prk. Orchids, Domingo Village | M. Poblacion | 750000 | 2014-09-01 | 2015-03-01 | 100% |  |  | Completed per POW
223-09-14 | Fencing of Schools @ San Agustin Elem. School | San Agustin | 600000 | 2014-10-01 | 2015-02-28 | 100% |  |  | Completed per POW
251-11-14 | Rehabilitation/ Construction of Drainage (w/out cover) @ Purok Elvi | Pagsabangan | 1000000 | 2015-12-01 | 2015-09-15 | 100% |  |  | Completed per POW
2015
032-01-15 | Cemetery Development- Construction of Tomb Niches & Childrens Tomb @ La Filipina Public Cemetery | La Filipina | 2500000 | 2015-01-21 |  | 89.84% | 2027114.36 |  | On- going
052-02-15 | Rehabilitation & Construction of Drainage @ Capitol Ave. | Mankilam | 700000 | 2015-03-02 | 2015-07-31 | 100% | 633087.5 |  | Completed
133-03-15 | Rehabilitation & Covering of Drainage @ Mangga Elem. School | Visayan Village | 300000 | 2015-03-01 | 2015-06-15 | 100% | 245101 |  | Completed
152-03-15 | Rehabilitation of Box Culvert - Phase 1 @ Prk. 1 | Canocotan | 500000 | 2015-05-04 | 2015-09-15 | 100% |  |  | Completed
153-03-15 | Rehabilitation of Box Culvert - Phase 2 @ Prk. 1 | Canocotan | 1000000 | 2015-05-04 | 2015-09-15 | 100% | 982726.54 |  | Completed
172-04-15 | Fabrication of Sports & Facilities |  | 100000 |  |  |  | 91010 |  | On- going
213-04-15 | Construction & Improvement of Gov't Building @ Public Terminal | Magugpo West | 500000 | 2015-06-01 | 2015-08-01 | 100% | 491185.13 |  | Completed
234-05-15 | Construction and Improvement of Gov't Building | Magugpo West | 700000 | 2015-08-16 |  | 37.9% | 612739 |  | On- going
251-06-15 | Renovation and Improvement of Warehouse, Engineering Service Center | Tipaz, Magugpo East | 1000000 | 2015-09-01 |  | 33.93% | 855096 |  | On- going
257-07-15 | Fabrication of Event Stage ( Movable Stage) Engineering Service Center | Magugpo East | 500000 |  |  |  | 431076.75 |  | On- going
261-06-15 | Construction of Tomb Niches @ Madaum Public Cemetery | Madaum | 200000 | 2015-07-02 | 2015-09-28 | 100% | 190167 |  | Completed
262-07-15 | Construction of Perimeter Tomb Niches @ Busaon Public Cemetery | Busaon | 300000 | 2015-07-08 | 2015-09-28 | 100% | 267687 |  | Completed
266-07-15 | Repair & Maintence of City Health Office ( Pharmacy Office) | Magugpo South | 59000 |  |  |  | 42653 |  | On- going
267-07-15 | Repair & Maintence of City Health Office (Laboratory) | Magugpo South | 26000 |  |  |  | 17974 |  | On- going
268-07-15 | Repair & Maintence of City Health Office (Administrative Office) | Magugpo South | 40000 |  |  |  | 26774 |  | On- going
269-07-15 | Repair & Maintence of City Health Office ( Office of CHO) | Magugpo South | 33000 |  |  |  | 22630 |  | On- going
270-07-15 | Repair & Maintence of City Health Office (Balik Sigla Program) | Magugpo South | 21000 |  |  |  | 14152 |  | On- going
274-07-15 | Rehabilitation/Construction of Drainage @ Prk. 3D, RTU Village (main drainage) | Apokon | 1000000 | 2015-07-21 |  | 35% | 724567.5 |  | On- going
276-07-15 | Rehabilitation/ Construction of Drainage (w/out cover) @ Prk. 2-A | La Filipina | 1000000 | 2015-08-11 |  | 49.14% | 756060.25 |  | On- going
278-07-15 | Rehabilitation/ Construction of Drainage (w/out cover) @ Daneco Sudb. | Magugpo East | 1620000 | 2015-08-01 |  | 67.62% | 1158044.75 |  | On- going
279-07-15 | Rehabilitation/ Construction of Drainage (w/out cover) @ Prk. Buli to Prk. Bunga- Cogon | Visayan Village | 500000 | 2015-08-17 |  | 54.83% | 338393.5 |  | On- going
280-07-15 | Rehabilitation/ Construction of Drainage (w/out cover) @ Walohan | Magugpo North | 500000 | 2015-08-11 |  | 49.38% | 370592.5 |  | On- going
281-07-15 | Construction of Perimeter Tomb Niches & Perimeter Bone Niches @ Pagsabangan Public Cemetery | Pagsabangan | 500000 | 2015-09-01 |  | 39.97% | 299391.37 |  | On- going
282-07-15 | Rehabilitation/ Construction of Drainage (w/out cover) @ Prk. Carig | Mankilam | 1000000 | 2015-09-01 |  | 46.35% | 316381.5 |  | On- going
283-07-15 | Rehabilitation/ Construction of Drainage (w/out cover) @ Prk. Daisy, Rabe Compound | Visayan Village | 200000 |  |  |  | 135995 |  | POW Approved
284-07-15 | Rehabilitation & CHB Lining of Drainage (w/out cover) @ Prk. Waling- waling | Visayan Village | 135000 |  |  |  | 88750 |  | For Implementation
302-08-15 | Construction of Drainage Rehabilitation/ Construction (w/out cover) @ Purok Diamond 1 | Magugpo North | 500000 | 2015-09-01 |  | 20% | 308470 |  | On- going
306-08-15 | Proposed Construction of Shed for Assorted Animals @ Energy Park | Apokon | 165000 |  |  |  | 130928 |  | POW Approved
310-08-15 | Rehabilitation/ Construction of Drainage (w/out cover) @ Prk. Kalamboan - Prk. 9 | La Filipina | 500000 |  |  |  | - |  | POW Approved
311-08-15 | Construction of Drainage- Rehabilitation of Drainage (w/out cover) @ Mandapaan | New Balamban | 700000 |  |  |  | - |  | POW Approved
New City Hall
160-04-15 | Completion of New City Hall Building- Mezzanine Works | Apokon | 1224800 | 2015-06-17 | 2015-09-30 | 100% | 1113424 |  | Completed
161-04-15 | Completion of New City Hall Bldg.- Drywall Partition Works | Apokon | 1953700 |  |  | 24.12% | 1599999.93
162-04-15 | Completion of New City Hall Building- Roofing Works | Apokon | 7939000 | 2015-06-17 |  | 80.59% | 5778267.37 |  | On- going
163-04-15 | Completion of New City Hall Building- Electrical Works | Apokon | 34055000 | 2015-06-22 |  | 84.09% | 26033217 |  | On- going
164-04-15 | Completion of New City Hall Building- Tile Works | Apokon | 3691400 | 2015-06-17 |  | 96.47% | 3237426 |  | On- going
165-04-15 | Completion of New City Hall Building- Ceiling Works | Apokon | 6731500 | 2015-08-24 |  | 32.54% | 1991489 |  | On- going
166-04-15 | Completion of New City Hall Building- Steel Handrail Works | Apokon | 196100 | 2015-08-10 | 2015-10-30 | 83.9% | 149567 |  | On- going
167-04-15 | Completion of New City Hall Building- Door Works | Apokon | 2733000 | [5 empty] | For Implementation
168-04-15 | Completion of New City Hall Building- Plumbing Works | Apokon | 2483000 | 2015-07-02 | 2015-09-30 | 100% | 2257248 |  | Completed | 59977266.75
169-04-15 | Completion of New City Hall Building-Aluminum Composite Panel Works | Apokon | 1493600 | 2015-06-29 | 2015-10-15 | 96.63% | 1312072.1 |  | On- going
170-04-15 | Completion of New City Hall Building- Glass Works | Apokon | 13179000 | 2015-09-07 | 2015-11-15 | 56.64% | 6786468 |  | On- going
171-04-15 | Completion of New City Hall Building- Mechanical works | Apokon | 12624000 | 2015-06-29 | 2015-10-30 | 84.68% | 9718088.35 |  | On- going
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
Prepared by: |  |  |  | Attested by:
| NORHANIAH S. DISOMA, CPA |  |  |  | RODILIO S. DINOPOL, CE
| Clerk I |  |  |  | Project Monitoring In- Charge
Noted by: |  |  |  | Approved by:
| ARCADIA E. YLANAN, CPA, MBA |  |  |  | ALLAN L. RELLON, DPA, Ph.D.
| City Budget Officer |  |  |  | City Mayor

## CAPITAL OUTLAY
FDP For 7 - Capital Outlay
Republic of the Philippines
Province of Davao del Norte
City of Tagum
OFFICE OF THE CITY BUDGET OFFICER
PROJECT MONITORING REPORT
CAPITAL OUTLAY
For the 3rd Quarter, CY 2015
Province, City or Municipality: TAGUM CITY
Ref No. | Particulars | Location | Total Cost | Date Started | Target Completion Date | % of Completion | Total Cost Incurred to Date | No. of Extensions, if any | Remarks
016-01-14 | Completion of two- storey school building @ Tagum City Trade School | Apokon | 500000 | 2014-03-01 | 2015-05-31 | 100% |  |  | Completed
017-01-14 | Construction of Comfort Room at New 2- Storey School Building Tagum City Trade School | Apokon | 300000 | 2014-03-01 | 2015-06-15 | 100% |  |  | Completed
028-02-14 | School Fencing at Bincungan Elem. School | Bincungan | 170000 | 2014-02-17 | 2015-01-17 | 100% |  |  | Completed per POW
029-02-14 | School Fencing at Madaum Elem. School | Madaum | 330000 | 2014-02-17 | 2015-01-15 | 100% |  |  | Completed per POW
102-04-14 | Rehabilitation/ Construction of Drainage @ Prk. 6, Agan | Magdum | 500000 | 2015-03-09 | 2015-05-15 | 100% |  |  | Completed per POW
114-05-14 | Rehabilitation/ Construction of Drainage (w/out cover) @ Purok 6, Agan | Magdum | 500000 | 2015-03-09 | 2015-05-15 | 100% |  |  | Completed per POW
123-05-14 | Construction of Meat Processing Area @ New Public Market | M. West | 1000000 | 2014-08-01 |  | 70.32% |  |  | Suspended- Waiting for Addt'l Mat
126-05-14 | Construction of Bridges (Construction of Flat Slab & Pathways) | Nueva Fuerza | 500000 | 2014-09-01 | 2015-07-31 | 100% |  |  | Completed per POW
127-05-14 | Construction/ Completion of Multi-purpose Buliding Construction of Sanitation Vehicle Garage Phase 1 @ Motorpool Compound | Magugpo East | 800000 | 2014-07-25 | 2015-02-15 | 100% |  |  | Completed per POW
133-03-15 | Rehabilitation/ Covering of Drainage (Top Slab) @ Mangga Elementary School | Visayan Village | 300000 |  |  |  | 245101
139-06-14 | Rehabilitation/ Construction of Drainage @ Iga-uy, Durian Avenue | Madaum | 1000000 | 2015-09-09 | 2015-02-10 | 100% |  |  | Completed per POW
143-06-14 | Construction of 6 Temporary Classroom @ Tagum City Trade School | Apokon | 700000 | 2014-07-16 | 2015-02-10 | 100% |  |  | Completed per POW
178-07-14 | Rehabilitation/ Construction of Drainage @ Suaybaguio District | Magugpo North | 175000 | 2014-07-15 | 2015-01-31 | 100% |  |  | Completed per POW
179-07-14 | Construction of School Building Magugpo Pilot Central Elem. School | Magugpo South | 1730000 | 2014-08-16 | 2015-02-28 | 100% |  |  | Completed per POW
187-07-14 | Rehabilitation/ Construction of Drainage @ Prk. Cabadiangan | San Isidro | 450000 | 2014-10-10 | 2015-02-15 | 100% |  |  | Completed per POW
189-07-14 | Rehabilitation/ Construction of Drainage @ Prk. Santol | La Filipina | 500000 | 2014-11-01 | 2015-02-15 | 100% |  |  | Completed per POW
216-09-14 | Concreting of Roads @ Prk. Orchids, Domingo Village | M. Poblacion | 750000 | 2014-09-01 | 2015-03-01 | 100% |  |  | Completed per POW
223-09-14 | Fencing of Schools @ San Agustin Elem. School | San Agustin | 600000 | 2014-10-01 | 2015-02-28 | 100% |  |  | Completed per POW
251-11-14 | Rehabilitation/ Construction of Drainage (w/out cover) @ Purok Elvi | Pagsabangan | 1000000 | 2015-12-01 | 2015-09-15 | 100% |  |  | Completed per POW
2015
032-01-15 | Cemetery Development- Construction of Tomb Niches & Childrens Tomb @ La Filipina Public Cemetery | La Filipina | 2500000 | 2015-01-21 |  | 89.84% | 2027114.36 |  | On- going
052-02-15 | Rehabilitation & Construction of Drainage @ Capitol Ave. | Mankilam | 700000 | 2015-03-02 | 2015-07-31 | 100% | 633087.5 |  | Completed
133-03-15 | Rehabilitation & Covering of Drainage @ Mangga Elem. School | Visayan Village | 300000 | 2015-03-01 | 2015-06-15 | 100% | 245101 |  | Completed
152-03-15 | Rehabilitation of Box Culvert - Phase 1 @ Prk. 1 | Canocotan | 500000 | 2015-05-04 | 2015-09-15 | 100% |  |  | Completed
153-03-15 | Rehabilitation of Box Culvert - Phase 2 @ Prk. 1 | Canocotan | 1000000 | 2015-05-04 | 2015-09-15 | 100% | 982726.54 |  | Completed
172-04-15 | Fabrication of Sports & Facilities |  | 100000 |  |  |  | 91010 |  | On- going
213-04-15 | Construction & Improvement of Gov't Building @ Public Terminal | Magugpo West | 500000 | 2015-06-01 | 2015-08-01 | 100% | 491185.13 |  | Completed
234-05-15 | Construction and Improvement of Gov't Building | Magugpo West | 700000 | 2015-08-16 |  | 37.9% | 612739 |  | On- going
251-06-15 | Renovation and Improvement of Warehouse, Engineering Service Center | Tipaz, Magugpo East | 1000000 | 2015-09-01 |  | 33.93% | 855096 |  | On- going
257-07-15 | Fabrication of Event Stage ( Movable Stage) Engineering Service Center | Magugpo East | 500000 |  |  |  | 431076.75 |  | On- going
261-06-15 | Construction of Tomb Niches @ Madaum Public Cemetery | Madaum | 200000 | 2015-07-02 | 2015-09-28 | 100% | 190167 |  | Completed
262-07-15 | Construction of Perimeter Tomb Niches @ Busaon Public Cemetery | Busaon | 300000 | 2015-07-08 | 2015-09-28 | 100% | 267687 |  | Completed
266-07-15 | Repair & Maintence of City Health Office ( Pharmacy Office) | Magugpo South | 59000 |  |  |  | 42653 |  | On- going
267-07-15 | Repair & Maintence of City Health Office (Laboratory) | Magugpo South | 26000 |  |  |  | 17974 |  | On- going
268-07-15 | Repair & Maintence of City Health Office (Administrative Office) | Magugpo South | 40000 |  |  |  | 26774 |  | On- going
269-07-15 | Repair & Maintence of City Health Office ( Office of CHO) | Magugpo South | 33000 |  |  |  | 22630 |  | On- going
270-07-15 | Repair & Maintence of City Health Office (Balik Sigla Program) | Magugpo South | 21000 |  |  |  | 14152 |  | On- going
274-07-15 | Rehabilitation/Construction of Drainage @ Prk. 3D, RTU Village (main drainage) | Apokon | 1000000 | 2015-07-21 |  | 35% | 724567.5 |  | On- going
276-07-15 | Rehabilitation/ Construction of Drainage (w/out cover) @ Prk. 2-A | La Filipina | 1000000 | 2015-08-11 |  | 49.14% | 756060.25 |  | On- going
278-07-15 | Rehabilitation/ Construction of Drainage (w/out cover) @ Daneco Sudb. | Magugpo East | 1620000 | 2015-08-01 |  | 67.62% | 1158044.75 |  | On- going
279-07-15 | Rehabilitation/ Construction of Drainage (w/out cover) @ Prk. Buli to Prk. Bunga- Cogon | Visayan Village | 500000 | 2015-08-17 |  | 54.83% | 338393.5 |  | On- going
280-07-15 | Rehabilitation/ Construction of Drainage (w/out cover) @ Walohan | Magugpo North | 500000 | 2015-08-11 |  | 49.38% | 370592.5 |  | On- going
281-07-15 | Construction of Perimeter Tomb Niches & Perimeter Bone Niches @ Pagsabangan Public Cemetery | Pagsabangan | 500000 | 2015-09-01 |  | 39.97% | 299391.37 |  | On- going
282-07-15 | Rehabilitation/ Construction of Drainage (w/out cover) @ Prk. Carig | Mankilam | 1000000 | 2015-09-01 |  | 46.35% | 316381.5 |  | On- going
283-07-15 | Rehabilitation/ Construction of Drainage (w/out cover) @ Prk. Daisy, Rabe Compound | Visayan Village | 200000 |  |  |  | 135995 |  | POW Approved
284-07-15 | Rehabilitation & CHB Lining of Drainage (w/out cover) @ Prk. Waling- waling | Visayan Village | 135000 |  |  |  | 88750 |  | For Implementation
302-08-15 | Construction of Drainage Rehabilitation/ Construction (w/out cover) @ Purok Diamond 1 | Magugpo North | 500000 | 2015-09-01 |  | 20% | 308470 |  | On- going
306-08-15 | Proposed Construction of Shed for Assorted Animals @ Energy Park | Apokon | 165000 |  |  |  | 130928 |  | POW Approved
310-08-15 | Rehabilitation/ Construction of Drainage (w/out cover) @ Prk. Kalamboan - Prk. 9 | La Filipina | 500000 |  |  |  | - |  | POW Approved
311-08-15 | Construction of Drainage- Rehabilitation of Drainage (w/out cover) @ Mandapaan | New Balamban | 700000 |  |  |  | - |  | POW Approved
New City Hall
160-04-15 | Completion of New City Hall Building- Mezzanine Works | Apokon | 1224800 | 2015-06-17 | 2015-09-30 | 100% | 1113424 |  | Completed
161-04-15 | Completion of New City Hall Bldg.- Drywall Partition Works | Apokon | 1953700 |  |  | 24.12% | 1599999.93
162-04-15 | Completion of New City Hall Building- Roofing Works | Apokon | 7939000 | 2015-06-17 |  | 64.31% | 5207724.28 |  | On- going
163-04-15 | Completion of New City Hall Building- Electrical Works | Apokon | 34055000 | 2015-06-22 |  | 76.48% | 23682735.65 |  | On- going
164-04-15 | Completion of New City Hall Building- Tile Works | Apokon | 3691400 | 2015-06-17 |  | 96.47% | 3237426 |  | On- going
165-04-15 | Completion of New City Hall Building- Ceiling Works | Apokon | 6731500 | 2015-08-24 |  | 10.06% | 615450 |  | On- going
166-04-15 | Completion of New City Hall Building- Steel Handrail Works | Apokon | 196100 | 2015-08-10 | 2015-10-30 | 83.9% | 149567 |  | On- going
167-04-15 | Completion of New City Hall Building- Door Works | Apokon | 2733000 | [5 empty] | For Implementation
168-04-15 | Completion of New City Hall Building- Plumbing Works | Apokon | 2483000 | 2015-07-02 | 2015-09-30 | 100% | 2257248 |  | Completed | 55701217.68
169-04-15 | Completion of New City Hall Building-Aluminum Composite Panel Works | Apokon | 1493600 | 2015-06-29 | 2015-10-15 | 96.63% | 1312072.1 |  | On- going
170-04-15 | Completion of New City Hall Building- Glass Works | Apokon | 13179000 | 2015-09-07 | 2015-11-15 | 47.2% | 5655390 |  | On- going
171-04-15 | Completion of New City Hall Building- Mechanical works | Apokon | 12624000 | 2015-06-29 | 2015-10-30 | 84.68% | 10870180.72 |  | On- going
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
Prepared by: |  |  |  | Attested by:
| NORHANIAH S. DISOMA, CPA |  |  |  | RODILIO S. DINOPOL, CE
| Clerk I |  |  |  | Project Monitoring In- Charge
Noted by: |  |  |  | Approved by:
| ARCADIA E. YLANAN, CPA, MBA |  |  |  | ALLAN L. RELLON, DPA, Ph.D.
| City Budget Officer |  |  |  | City Mayor

## TRUST FUND
FDP Form 7 - Trust Fund
Republic of the Philippines
Province of Davao del Norte
City of Tagum
OFFICE OF THE CITY BUDGET OFFICER
PROJECT MONITORING REPORT
TRUST FUND
For the 3rd Quarter, CY 2015
Province, City or Municipality: TAGUM CITY
Ref No. | Particulars | Location | Total Cost | Date Started | Target Completion Date | % of Completion | Total Cost Incurred to Date | No. of Extensions, if any | Remarks
053-02-15 | DSWD- Core Shelter Assistance Program |  | 2000000 | 2015-05-28 |  | 95% | 1697973.5 |  | On-going
149-03-15 | Concreting of Road Iga Uy Resettlement | Madaum | 1205689.2 | [5 empty] | Completed
154-03-15 | Construction/ Completion of School Building National Child Development Center | M. Poblacion | 21000 | 2015-06-16 | 2015-07-31 | 100% | 19125 |  | Completed
190-04-15 | Repair & Maintenance of School Building @ Madaum Elem. School | Madaum | 250000 | 2015-05-22 | 2015-08-31 | 100% | 239884.95 |  | Completed
191-04-15 | Repair & Maintenance of School Building @ Laureta Elem. School | San Miguel | 250000 | 2015-04-18 | 2015-08-11 | 100% | 233540 |  | Completed
192-04-15 | Repair & Maintenance of School Building @ Visayan Village Elem. School | Visayan Village | 250000 | 2015-04-18 | 2015-08-31 | 100% | 233232 |  | Completed
193-04-15 | Repair & Maintenance of School Building @ Magugpo Pilot Imelda E/S | M. South | 250000 | 2015-04-16 | 2015-09-15 | 100% | 239973 |  | Completed
194-04-15 | Repair & Maintenance of School Building @ Jose Tuason Memorial High School | Madaum | 250000 | 2015-04-25 | 2015-08-31 | 100% | 211610 |  | Completed
195-04-15 | Repair & Maintenance of School Building @ Laureta National H/S | San Miguel | 250000 | 2015-04-18 | 2015-08-11 | 100% | 243531.94 |  | Completed
196-04-15 | Repair & Maintenance of School Building @ Apokon E/S | Apokon | 250000 | 2015-04-20 | 2015-07-31 | 100% | 242441 |  | Completed
197-04-15 | Repair & Maintenance of School Building @ Mankilam Elem School | Mankilam | 250000 | 2015-04-18 | 2015-07-06 | 100% | 213884 |  | Completed
198-04-15 | Repair & Maintenance of School Building @ Magugpo Central Elem. School | M. South | 250000 | 2015-04-20 | 2015-08-31 | 100% | 232480 |  | Completed
199-04-15 | Repair & Maintenance of School Building @ Tagum City National Comprehensive H/S | Mankilam | 250000 | 2015-04-18 |  | 50% | 235279.3 |  | On-going
200-04-15 | Repair & Maintenance of School Building @ Union Elem. School | Mankilam | 250000 | 2015-04-18 | 2015-08-31 | 100% | 214716 |  | Completed
201-04-15 | Repair & Maintenance of School Building @ La Filipina Elem. School | La Filipina | 250000 | 2015-04-16 | 2015-09-22 | 100% | 239469 |  | Completed
202-04-15 | Repair & Maintenance of School Building @ Rizal Elem. School | M. South | 250000 | 2015-04-18 |  | 97% | 226397.5 |  | On-going
203-04-15 | Repair & Maintenance of School Building @ Don Ricardo Briz Elem. School | M. East | 250000 | 2015-04-18 | 2015-06-15 | 100% | 238819 |  | Completed
204-04-15 | Repair & Maintenance of School Building @ Mangga Elem. School | Visayan Village | 250000 | 2015-04-16 | 2015-08-31 | 100% | 235219 |  | Completed
205-04-15 | Repair & Maintenance of School Building @ La Filipina National H/S | La Filipina | 250000 | 2015-04-16 | 2015-07-31 | 100% | 220659.3 |  | Completed
206-04-15 | Repair & Maintenance of School Building @ Tagum National Trade School | Apokon | 250000 | 2015-04-20 | 2015-08-31 | 100% | 239056.5 |  | Completed
207-04-15 | Repair & Maintenance of School Building @ Tagum City National H/S | Visayan Village | 250000 | 2015-04-16 | 2015-08-31 | 100% | 231651 |  | Completed
246-06-15 | Construction of Rice Mill Housing @ Prk. Bagong Silang | Pagsabangan | 250000 | 2015-10-05 | 2015-12-15 | 3% | 160574 |  | On-going
295-08-15 | Vermi Rehab Facility @ Prk. Ipil-Ipil | San Agustin | 130000 | 2015-10-05 | 2015-11-15 | 20% |  |  | On-going
256-06-15 | Concreting of Roads @ Prk. Mauswagon | M. South | 538000 | [5 empty] | POW Approved
298-08-15 | Concreting of Roads @ Prk. Alvarida | Pagsabangan | 2000000 | 2015-08-13 |  |  | 609330.62 |  | Suspended due to Road Right Of Way conflict
299-08-15 | Concreting of Roads @ Sitio Kasilak | San Agustin | 2000000 | 2015-08-13 |  |  | 1137898 |  | On-going
300-08-15 | Concreting of Roads @ Prk. Alambre | San Isidro | 2000000 | 2015-08-13 |  |  | 1039509 |  | On-going
301-08-15 | Concreting of Roads @ Brgy. San Isidro- Brgy. Canocotan (Tano Area) Road | San Isidro | 2000000 | 2015-08-13 | 2015-12-15 | 15% | 1149255.5 |  | On-going
322-09-15 | Construction/ Completion of Multi-purpose Building, Pasalubong Center | Apokon | 3000000 | 2015-09-14 | 2015-11-15 | 30% | 2697234.2 |  | On-going
001-01-14 | DepEd- Development of School Furnitures 2014 | Various Schools | 1000000 | 2014-01-06 | 2015-08-05 | 100% | 943915.5 |  | Completed
059-03-14 | Fabrication of School Furniture 2014 B | Various Schools | 900000 | 2014-03-04 | 2015-04-07 | 100% | 893926 |  | Completed
090-04-14 | NMIS- Construction of Tagum City's New "AA" Slaughter House | Madaum | 10000000 | 2014-05-01 | 2015-05-31 | 98.71% | 9348730.57 |  | On-going
148-06-14 | Fabrication of School Furniture 2014 A | Various Schools | 1000000 | 2014-06-23 | 2015-08-11 | 100% | 999922.5 |  | Completed
149-03-15 | Concreting of Road Iga Uy Resettlement | Madaum | 1205689.2 | 2015-08-01 | 2015-12-15 | 5% |  |  | On-going
154-06-14 | Rehabilitation/ Construction of Drainage @ Wakan Relocation Site | Brgy. San Isidro | 826576 | 2014-09-01 | 2015-03-15 | 100% | 805670 |  | Completed
235-10-14 | CDRRMO- Other Rescue and Response Equipment Construction of Trillon Tower | Magugpo East | 450000 | 2014-11-10 | 2015-04-15 | 100% | 415372.72 |  | Completed
242-10-14 | Tagum City Local Road Funds CY 2013, San Miguel Road | San Miguel | 695223.91 | 2014-11-10 |  | 100% | 595132.28 |  | Completed
243-10-14 | Tagum City Local Road Funds CY 2013, Timog Road | Visayan Village | 919461.75 | 2014-11-16 | 2015-04-30 | 100% | 891667.92 |  | Completed
244-10-14 | Tagum City Local Road Funds CY 2013, Villa Paraiso | Visayan Village | 1444455.34 |  |  | 100% | 1433658.73 |  | Completed
268-11-14 | DA- DIDP, Concreting of Prk. 2 Brgy. Liboganon | Liboganon | 3552480.14 | 2015-01-05 | 2015-07-31 | 100% | 2778101.96 |  | Completed
276-12-14 | Tagum City Local Road Funds CY 2013, Pioneer Avenue | Brgy. Poblacion | 2873219.52 |  |  | 100% | 2340874.1 |  | Completed
010-01-13 | Asphalting of Laureta School Road towards Resettlement Road. Section | San Miguel | 970000 | 2013-07-30 | 2014-09-24 | 100% | 958122.58 |  | Completed
011-01-13 | Asphalting of Bincungan Interior Road System | Bincungan | 970000 | 2013-08-01 | 2014-09-24 | 100% | 29289.9 |  | Completed
012-01-13 | Asphalting of RTU Resettlement (Continuation) RD. Secc. | Apokon | 1484100 | 2013-08-15 | 2014-09-24 | 100% | 1478715.1 |  | Completed
148-04-13 | DepEd- Fabrication of School Furniture | Tagum City | 1722037.4 |  |  |  | - |  | Cancelled
154-05-13 | Concreting of Road at Visayan Village towards Jalandoni Subdivision | Visayan Village | 1120000 | 2013-08-05 | 2014-09-24 | 100% | 949837 |  | Completed
155-05-13 | Concreting of Road Iga Uy Resettlement Road Sect. | Madaum | 1120000 | 2013-08-05 | 2014-01-07 | 100% | 937510.98 |  | Completed
172-08-13 | DA BFAR- Proposed Construction of Multi Species Algal Tank, Plumbing & Electrical | Liboganon | 499800 | 2013-11-12 | 2015-10-01 | 100% | 485330.11 |  | Completed
173-08-13 | Proposed Construction of Saline Tilapia Hatchery | Brgy. Bincungan | 190640 | 2013-11-21 | 2015-10-01 | 100% | 165129.81 |  | Completed
175-08-13 | Proposed Construction of Multi Species (Larval Building) | Liboganon | 1635800 | 2013-11-12 | 2015-09-08 | 100% | 11598582.75 |  | Completed
174-08-13 | PROPOSED Construction of Multi Species (Reservoir/ Water Tank) | Liboganon | 223760 | 2013-11-12 | 2015-09-15 | 100% | 211493 |  | Completed
180-09-13 | Construction of Drainage Rehabilitation and CHB Lining of Drainage (w/o cover) @ Mankilam Creek (Tadena) | Mankilam | 1500000 | 2013-09-17 | 2014-08-13 | 100% | 1487304.82 |  | Completed
181-09-13 | Construction of Drainage Rehabilitation and CHB Lining of Drainage (w/o cover) @ San Miguel Creek (Fajardo) | San Miguel | 1000000 | 2013-09-17 | 2014-05-30 | 100% | 992606.5 |  | Completed
322-09-15 | Const./Completion of Multi-Purpose Bldg., PASALUBONG CENTER | Apokon | 3000000 | 2015-09-14 | 2015-10-31 | 67% | 2697234.2 |  | On-going
AD-300-14-008 | DENR- National Greening Program | Tagum City | 37500 |  |  | 100% | 37500 |  | Completed
AD-30014-040 | DENR- National Greening Program | Tagum City | 93750 |  |  | 100% | 93750 |  | Completed
AD-300-14-064 | DENR- National Greening Program | Tagum City | 93750 |  |  | 100% | 93750 |  | Completed
AD-300-14-017 | Operation Hugpong na Serbisyo | Tagum City | 50000 |  |  | 100% | 38641 |  | Completed
AD-300-14-026 | Hugpong Serbisyo para sa Tagumenyos Post Activity Assessment, Feedbacking and Evaluation | Tagum City | 160000 |  |  | 100% | 148232 |  | Completed
AD-300-14-034 | For the Meals of Volunteers and Manpower of Hugpong na Sebisyon para sa Tagumenyos | Tagum City | 50000 |  |  | 100% | 46869 |  | Completed
AD-300-15-013 | Musikahan Festival 2015 | Tagum City | 177500 |  |  | 100% | 176971 |  | Completed
AD-300-15-015 | Musikahan Festival 2015 | Tagum City | 190000 |  |  | 100% | - |  | Completed
AD-300-14-12 | Musikahan Festival 2015 | Tagum City | 143000 |  |  | 100% | 138400 |  | Completed
AD-300-14-009 | Musikahan Festival 2015 | Tagum City | 215500 |  |  | 100% | 211000 |  | Completed
AD-300-14-016 | Musikahan Festival 2015 | Tagum City | 150000 |  |  | 100% | 144700 |  | Completed
AD-300-14-042 | Musikahan Festival 2015- PAGCOR | Tagum City | 49229.2 |  |  | 100% | 43299.2 |  | Completed
AD-300-14-043 | 1st Mutya ng Tagum 2013- PAGCOR | Tagum City | 99314 |  |  | 100% | 57158.95 |  | Completed
AD-300-14-046 | Barangay Musikahan | Tagum City | 10000 |  |  | 100% | 8075 |  | Completed
AD-300-14-047 | Pre Kadagayaan Whole year campaign | Tagum City | 10514 |  |  | 100% | 10514 |  | Completed
AD-300-14-029 | Participation to Kadagayaan Festival | Tagum City | 50000 |  |  | 100% | 49680 |  | Completed
AD-300-14-032 | Participation to Kadagayaan Festival 2 | Tagum City | 50000 |  |  | 100% | 49200 |  | Completed
AD-300-14-035 | Kadagayaan Festival Post Evaluation & 2015 Planning | Tagum City | 31160 |  |  | 100% | 30659.66 |  | Completed
439-007-0013 | Fiesta Trade Fair | Tagum City | 77200 |  |  | 100% | 76710 |  | Completed
AD-300-14-028 | Donation for Fun Run of Peace | Tagum City | 28950 |  |  |  | -
AD-300-14-065 | Literacy Coordinating Council- Cash Award (Social Services) | Tagum City | 54000 |  |  |  | -
AD-300-14-071 | Literacy Coordinating Council- Cash Award (Various Literacy Programs & Projects) | Tagum City | 146000 |  |  |  | 134726.52
AD-300-14-083 | CMO- Business License Section- Businesss for Licensing and Inspection Fee | Tagum City | 65120 |  |  | 100% | 64200 |  | Completed
AD-300-15-011 | CMO- Business License Section- Businesss for Licensing and Inspection Fee | Tagum City | 180000 |  |  | 100% | 166218 |  | Completed
AD-300-14-069 | DILG- Galing Pook Award Night Market | Tagum City | 35000 |  |  | 81% | 25343 |  | On-going
AD-300-14-082 | DILG- Galing Pook Award Night Market | Tagum City | 50480 |  |  | 100% | 50480 |  | Completed
AD LABOR-14-007 | Saint Peter Green Program | Tagum City | 872310 |  |  | 100% | 844476.17 |  | Completed
AD LABOR-14-013 | Saint Peter Green Program | Tagum City | 472250 |  |  | 100% | 457215 |  | Completed
AD LABOR-14-044 | Saint Peter Green Program | Tagum City | 472250 |  |  | 100% | 275220 |  | Completed
AD LABOR-15-003 | Saint Peter Green Program | Tagum City | 472250 |  |  | 100% | 322452 |  | Completed
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
Prepared by: |  |  |  | Attested by:
| NORHANIAH S. DISOMA, CPA |  |  |  | RODILIO S. DINOPOL, CE
| Clerk I |  |  |  | Project Monitoring In- Charge
Noted by: |  |  |  | Approved by:
| ARCADIA E. YLANAN, CPA, MBA |  |  |  | ALLAN L. RELLON, DPA, Ph.D.
| City Budget Officer |  |  |  | City Mayor

## 20% Dev't Fund
FDP Form 7 - 20% Development Fund
Republic of the Philippines
Province of Davao del Norte
City of Tagum
OFFICE OF THE CITY BUDGET OFFICER
PROJECT MONITORING REPORT
20% Component of IRA Utilization
For the 4th Quarter, CY 2015
Province, City or Municipality : TAGUM CITY
Ref No. | Particulars | Location | Total Cost(PhP) | Date Started | Target Completion Date | % of Completion | Total Cost Incurred to Date(PhP) | No. of Extensions, if any | Remarks
PROJECTS/PROGRAMS CY 2015
014-01-15 | Completion of New Tagum City Hall Building | Apokon | 158284439.71 | 2015-06-17 | 2015-12-25 | 65.79% | 52811646.82 |  | On-going
016-01-15 | Rehabilitation of Asphalted Roads @ various location | Various Barangays Tagum City | 1500000 | 2015-01-05 | 2015-12-29 | 96% | 1080097.7 |  | On- going
018-01-15 | Electrification Program- Gad | Various Barangays Tagum City | 180000 | 2015-03-02 | 2015-12-29 | 75% | 138901 |  | On- going
023-01-15 | Installation of Lighting Facilities @ Villa Consuelo to Maco Bridge | Apokon | 615000 | 6/16/16 | 8/31/15 | 40.78% | 611572.75 |  | On-going
024-01-15 | Installation of Lighting Facilities @ Cristina Homes to Villa Consuelo | Apokon | 315000 | 5/15/15 | 6/30/15 | 82.96% | 303627.83 |  | On-going
028-01-15 | Concreting of Road @ Engineering Service Center | Magugpo East | 714000 | 2015-07-01 | 2015-11-30 | 55.67% | 605335.04 |  | On-going
029-01-15 | Cocreting of Roads @ 5th Avenue Misa District | Magugpo South | 500000 | 2015-02-01 | 2015-05-31 | 100% | 457353.72 |  | Completed
030-01-15 | Concreting of Roads @ 4th Avenue, Misa District | Magugpo South | 500000 | 2015-05-01 | 2015-07-31 | 100% | 453781.27 |  | Completed
038-02-15 | Concreting of Roads @ Pisces & Capricorn St., Daneco Village | Magugpo East | 500000 | 2015-04-01 | 2015-07-31 | 100% | 487093.14 |  | Completed
039-02-15 | Concreting of Roads @ Aala Road ( Rear of Davao del Norte Sports Complex ) | Mankilam | 1400000 | 2015-02-14 | 2015-05-31 | 100% | 1211663.07 |  | Completed
040-02-15 | Const'n. / Rehab. Of MP Pavement - Construction of Concrete Basketball Court @ Prk. Sto. Niño | Pagsabangan | 275000 | 2015-04-16 | 2015-05-15 | 100% | 239819 |  | Completed
042-02-15 | Const'n. / Rehab. Of MP Pavement - Concrete Overlay of Existing Basketball Court @ Prk. Maharlika, Senangote 1 | Magugpo East | 135000 | 2015-04-06 | 2015-07-31 | 100% | 125276 |  | Completed
044-02-15 | Dev't. of Parks & Highways - PROPOSED JOGGING LANE @ 2loy Car Aircon Specialist to Across Tionko Village Entrance | Brgy. Visayan Village - Brgy. Canocotan | 2000000 | 2015-05-11 | 2016-03-31 | 50% | 1538913 |  | On-going
046-02-15 | Const'n. / Rehab. Of MP Pavement - Construction of Concrete of Existing Basketball Court @ Garciaville Gym | Magugpo South | 190000 | 2015-03-18 | 2015-04-30 | 100% | 176108 |  | Completed
047-02-15 | Const'n. / Rehab. Of MP Pavement - Construction of Concrete Volleyball Court @ Laureta National High School | San Miguel | 230000 | 5/12/15 | 7/15/15 | 100% | 217137.2 |  | Completed
048-02-15 | Const'n. / Rehab. Of MP Pavement - CONSTRUCTION OF CONCRETE BASKETBALL COURT @ Prk. Cebole | Visayan Village | 275000 | 2015-03-20 | 2015-05-15 | 100% | 232721 |  | Completed
049-02-15 | Construction / Rehab. Of Multi-Purpose Pavement Concrete Overlay of Existing Basketball Court @ Prk. 5-A | La Filipina | 140000 | 3/24/15 | 5/8/15 | 100% | 129701 |  | Completed
050-02-15 | Const. / Rehab. Of Multi-Purpose Pavement - CONSTRUCTION OF CONCRETE BASKETBALL COURT @ Prk. 28 Coop A-C | Madaum | 275000 | 2015-03-20 | 2015-04-30 | 100% | 257755 |  | Completed
051-02-15 | Concreting of Roads @ Purok 1 | Canocotan | 1000000 | 2015-04-16 | 2015-07-31 | 100% | 844579.25 |  | Completed
055-02-15 | Asphalting of Roads @ Prk. Camia-Prk.Suaybaguio, Brgy. M-North | Magugpo North | 500000 | 4/1/2015 | 2015-12-29 | 47% | 363822.94 |  | On-going
061-03-15 | Const'n. / Rehab. Of MP Pavement - Concrete Overlay of Existing Basketball Court @ Prk. Marangal, Sison Subdivision | Magugpo South | 235000 | 2015-04-16 | 2015-05-15 | 100% | 216822.27 |  | Completed
124-03-15 | Electrification Program-2015 Palarong Pambansa Playing Venue at Rotary Park (Tennis Court & Dog Park) | Magugpo Poblacion | 70360 |  |  |  | 70132 |  | Completed
125-03-15 | Electrification Program-2015 Palarong Pambansa Playing Venue at Mankilam Gym | Mankilam | 65122 |  |  | 100% | 64874 |  | Completed
126-03-15 | Electrification Program-2015 Palarong Pambansa Playing Venue at Tagum Trade & Cultural Center | Magugpo Poblacion | 139004 |  |  | 100% | 138152 |  | Completed
127-03-15 | Installation of Lighting Facilities for Playing Magugpo North Gym | Brgy. North | 36218 |  |  |  | 34514 |  | Completed
128-03-15 | Electrification Program-2015 Palarong Pambansa Playing Venue at Visayan Village Gym | Visayan Village | 50708 |  |  |  | 50540 |  | Completed
129-03-15 | Electrification Program-2015 Palarong Pambansa Playing Venue at USEP Gym | Apokon | 139004 |  |  | 100% | 138940 |  | Completed
127-03-15 | Electrification Program-2015 Palarong Pambansa Playing Venue at Magugpo North Gym | Magugpo North | 36218 |  |  | 100% | 34514 |  | Completed
130-03-15 | Electrification Program-2015 Palarong Pambansa Playing Venue at Apokon Gym | Apokon | 36256 |  |  | 100% | 36112 |  | Completed
131-03-15 | Electrification Program-2015 Palarong Pambansa Playing Venue at Rotary Gym | Magugpo Poblacion | 139004 |  |  | 100% | 138152 |  | Completed
132-03-15 | Electrification Program-2015 Palarong Pambansa Playing Venue at E-Park | Apokon | 78398 |  |  | 100% | 78175 |  | Completed
134-03-15 | Construction / Completion of Multi-Purpose Building ( COMPLETION OF BARANGAY HALL ) @ Purok Sampaguita | Bincungan | 900000 |  |  |  | 705953 |  | POW Revised
135-03-15 | Asphalting of Roads @ Service Road Tacip | Magugpo North | 600000 | 2015-08-01 | 2015-12-29 | 5.3% | 456221.37 |  | On- going
136-03-15 | Asphalting of Roads @ Prk. Durian | Mankilam | 500000 | 2015-08-01 | 2015-12-29 | 4.5% | 370742.1 |  | On- going
137-03-15 | Asphalting of Roads @ Service Road-Sobrecary-Bonifacio | Magugpo Poblacion | 600000 |  |  |  | 463861.94 |  | On- going
138-03-15 | Asphalting of Roads @ Service Road in front of CAP-Shell Station | Magugpo Poblacion | 600000 | 2015-08-01 | 2015-12-29 | 5% | 435792.53 |  | On- going
139-03-15 | Asphalting of Roads @ Prk. Sunshine, J Village | Visayan Village | 500000 | 4/1/2015 | 5/15/2015 | 100% | 469752.19 |  | Completed
140-03-15 | Development of San Agustin Eco-Park -Construction of Pathway | San Agustin | 500000 | 2015-05-11 | 2015-09-15 | 95% | 471512 |  | On going
141-03-15 | Development of San Agustin Eco-Park-Completion of Comfort Room | San Agustin | 100000 |  |  | 15% | 62822 |  | On-going
142-03-15 | Development of New Balamban Bird Park-Construction of Pathway | New Balamban | 150000 |  |  | 90% | 134213 |  | On-going
145-03-15 | Concreting of Roads-Prk.1 Rizal | Canocotan | 1000000 | 2015-07-01 | 2015-12-31 | 63.22% | 797433 |  | On-going
146-03-15 | Concreting of Roads-Parking Area, Pasalubong Center (E-Park) | Apokon | 2000000 | 2015-04-01 |  | 97% |  |  | On-going
147-03-15 | Asphalting of Roads @ Prk.Waling-Waling, Macasero | Visayan Village | 500000 | 4/1/2015 | 5/4/2015 | 100% | 479430.93 |  | Completed
150-03-15 | Concreting of Roads @ Prk. 1-A (Road going Bridges Academy) | Brgy. San Miguel | 300000 | 2015-05-16 | 2015-08-31 | 100% | 268269 |  | Completed
151-03-15 | Construction of Parks & Plaza in Barangay & Subdivision-Sison Subdivision | Magugpo South | 100000 | 6/16/15 | 9/15/15 | 98.48% | 67798 |  | Physically Completed
152-03-15 | Rehabilitation/Const. of Drainage | Canocotan | 500000 | 2015-05-04 | 2015-07-31 | 82.94% |  |  | On-going
173-04-15 | Concreting of Roads Budiongan-Tagum Nat'l High School | Visayan Village | 1000000 | 2015-05-16 | 2015-08-31 | 100% | 945678.27 |  | Completed
174-04-15 | Construction of 1-unit Gazebo @ Prk. Mandapaan | New Balamban | 275000 |  |  | 95% | 231333 |  | On-going
175-04-15 | Const./Completion of Multi-Purpose Bldg. (Purok Center) @ Prk. 6 | La Filipina | 100000 | 2015-05-08 |  | 95% | 92839.15 |  | On-going
176-04-15 | Construction/ Completion of Multi- purpose Bldg. | Visayan Village | 100000 | 2015-07-21 | 2015-10-21 | 74.4% | 99136.15 |  | On- going
177-04-15 | Const./Completion of Multi-Purpose Bldg. (Purok Center) @ Prk. E. Omila Compound | Apokon | 100000 | 2015-05-04 | 2015-06-30 | 100% | 95592.65 |  | Completed
178-04-15 | Const./Completion of Multi-Purpose Bldg. (Purok Center) @ Prk. Mahogany | Visayan Village | 100000 | 2015-06-09 | 2015-08-10 | 100% | 94567.65 |  | Completed
179-04-15 | Constructio of Parks & Plazas in Barangay & Subdivision, Brgy. Hall | San Isidro | 100000 | 2015-07-09 | 2015-09-15 | 100% |  |  | Completed
180-04-15 | Construction of Parks & Plazas in Barangay & Subdivision, La Filipina Nat'l. High School | La Filipina | 200000 | 6/16/15 | 09/15/15 | 100% | 171532 |  | Completed
181-04-15 | Const./Completion of Multi-Purpose Bldg. (Purok Center) @ Prk. Pinya | Visayan Village | 100000 | 2015-07-15 | 2015-08-30 | 100% | 84886.5 |  | Completed
182-04-15 | Asphalt Operation (Cost of Construction- MOOE) @ USEP Tagum Compound | Apokon | 2005099 | 2015-05-01 | 2015-06-30
183-04-15 | Asphalt Operation (Cost of Construction- MOOE) @ USEP Mampesing Compound, Mabini | Comval | 1494901 | 2015-06-01 | 2015-07-31 | 90%
184-04-15 | Development of Energy Park Completion of K-9 Building- SB1 | Apokon | 65000 |  |  |  | 62437 |  | Completed
185-04-15 | Development of Energy Park - Repainting of Front Fence- SB1 | Apokon | 200000 |  |  | 100% | 188663 |  | Completed
186-04-15 | Const./Completion of Cultural Communities Education Center @ Prk. Gumamela | Bincungan | 100000 | 2015-06-22 | 2015-08-15 | 98.81% | 83117.5 |  | On- going
187-04-15 | Construction/ Completion of Multi- Purpose Gym (Construction og Stage) @ Makabayan Village | San Isidro | 900000 | 2015-06-01 | 2015-08-31 | 91.69% |  |  | On-going
188-04-15 | Const./Completion of Multi-Purpose Bldg. (Purok Center) @ Prk. 3-G, RTU Village | Apokon | 100000 | 2015-06-09 | 2015-08-10 | 100% | 88762 |  | Completed
189-04-15 | Fencing of Slaughterhouse | Magdum | 800000 | 2015-06-01 | 2015-11-15 | 93.42% | 746503.85 |  | On-going
208-04-15 | Const./Completion of Cultural Communities Education Center (Madrasah) @ Prk. Cabadiangan | San Isidro | 320000 | 2015-06-01 | 2015-08-31 | 100% | 281041.4 |  | Completed
209-04-15 | Const./Completion of Cultural Communities Education Center @ Prk. Durian | San Isidro | 280000 | 2015-06-01 | 2015-08-31 | 100% | 213121.25 |  | Completed
210-04-15 | Const. of Waste Lagoon | Magdum | 500000 |  |  | 70% | 330720 |  | On- going
212-04-15 | Concreting of Roads @ Prk. Cogon | Visayan Village | 700000 | 2015-07-16 | 2015-10-31 | 84.12% | 599051.54 |  | On-going
031-01-15 | Water Development Program-Replacement of Jetmatic Pump | La Filipina | 50000 |  |  |  | 27145 |  | POW Approved
054-02-15 | Asphalting of Roads @ Prk.2-A. Suico Comp.,San Miguel | San Miguel | 600000 |  | 2015-12-29 |  | 369110 |  | For Implementation
215-04-15 | Water Development Program-Replacement of Jetmatic Pump | Apokon | 50000 |  |  |  | 27141 |  | For Implementation
216-04-15 | Water Development Prigram-Replacement of Jetmatic Pump | Visayan Village | 50000 |  |  |  | 27145 |  | For Implementation
217-04-15 | Water Development Program-Replacement of Jetmatic Pump | Nueva Fuerza | 50000 |  |  |  | 27141 |  | For Implementation
025-01-15 | Installation of Lighting Facilities @ New City Hall to Curvada, Apokon | Apokon | 390000 |  |  |  | 382544.75 |  | On-going
026-01-15 | Installation of Lighting Facilities @ Iglesia to Km.48 | Canocotan | 300000 |  |  |  | 232363 |  | For Implementation
027-01-15 | Installation of Lighting Facilities @ Uraya to Pagsabangan Cemetery | Mankilam | 300000 |  |  |  | 232101 |  | For Implementation
218-04-15 | Water Development Program-Replacement of Jetmatic Pump | Pagsabangan | 50000 |  |  |  | 27141 |  | For Implementation
219-04-15 | Water Development Program-Replacement of Jetmatic Pump | Cuambogan | 50000 |  |  |  | 27145 |  | For Implementation
041-02-15 | Dev't. of Parks & Highways - PROPOSED JOGGING LANE Across Tionko Village Entrance to Plywood Veneering Plant | Canocotan | 763807.79 | 2015-05-11 | 2015-12-31 | 70% | 697132 |  | On-going
220-04-15 | Water Development Program-Replacement of Jetmatic Pump | Mankilam | 50000 |  |  |  | 27145 |  | For Implementation
304-08-15 | Water Development Program-Construction and Installation of Jetmatic Pump @ Purok 8 | La Filipina | 60000 | 2015-08-03 | 2015-08-31 | 100% |  |  | Completed
290-80-15 | Construction of Dug Well with Iron Removal Filter | Pagsabangan | 80000 | 2015-08-06 | 2015-10-30 | 100% | 70421.29 |  | Completed
291-08-15 | Construction of Dug Well with Iron Removal Filter @ Purok Santan | Bincungan | 101000 | 2015-09-09 | 2015-10-28 | 34% | 71532 |  | On- going
292-08-15 | Const. and Rehab. of 4 units Jetmatic Pump | Cuambogan | 150000 | 2015-08-19 |  | 8% | 130872.92 |  | On- going
293-08-15 | Stainless Water Tank 7,000ltrs Cap. (Horizontal Type) @ Purok 6 | La Filipina | 250000 |  |  |  | 174475 |  | On- going
294-08-15 | Stainless Water Tank 7,000ltrs Cap. (Horizontal Type) @ Purok Waling2 | Bincungan | 246000 |  |  |  | 150674 |  | On- going
225-09-14 | Construction of Bus Stop & Waiting Shed @ Tionko Village | Canocotan | 80000 | 2014-10-13 | 2014-12-05 | 100% | 75010 |  | Completed
227-05-15 | Constuction of Parks & Plazas in Barangay & Subdivision, Laureta Nat'l. High School | San Miguel | 200000 | 6/16/15 | 8/30/15 | 92% | 183243 |  | On- going
228-05-15 | Concreting of Roads Country Homes, Blk. 12, 13 and 14 | Mankilam | 400000 | 2015-09-01 | 2015-11-15 | 80% | 263977 |  | On-going
229-05-15 | Signages @ Brgy. Apokon | Apokon | 50000 |  |  |  | 49425 |  | POW Approved
231-05-15 | Constuction of Parks & Plazas in Barangay & Subdivision, San Antonio De Padua Church Mel Village | Visayan Village | 100000 | 2015-08-01 | 2015-09-30 | 100% | 73542 |  | Completed
232-05-15 | Proposed Hog & Cattle Pen House | Magdum | 1300000 |  |  |  | 870547.86 |  | On- going
233-05-15 | Const./Completion of Cultural Communities Education Center (Madrasah) | Prk. Mangga, Pandapan | 300000 | 2015-07-20 | 2015-09-21 | 97.31% | 258791 |  | On- going
235-05-15 | Concreting of Roads Prk. Liwayway, 2nd Ave., Misa District | Magugpo South | 500000 | 2015-09-01 | 2015-11-30 | 60% | 392247.08 |  | On- going
243-06-15 | Construction/ Completion of Multi- purpose Bldg.- Repair of Visayan Barangay Hall (back portion) | Visayan Village | 100000 | 2015-06-16 | 2015-09-30 | 100% | 95739 |  | Completed
244-06-15 | Concreting of Roads@ Narisma Road | Magugpo South | 800000 |  |  |  | 615436.25 |  | POW Approved
245-06-15 | Boy Scout Landmark | Apokon | 400000 |  |  | 100% | 399900 |  | Physically Completed
247-06-15 | Concrete Tank Stand | Magdum | 450000 | 2015-08-16 | 2015-11-30 | 81.01% | 288507 |  | On- going
248-06-15 | Fencing of Slaughterhouse Phase 2 | Magdum | 200000 | 2015-10-01 | 2015-12-31 | 11.86% | 98607.75 |  | On- going
249-06-15 | Construction/ Completion of Multi- purpose Bldg.. ( Purok Center) @ Prk. 5-A | La Filipina | 100000 | 2015-07-15 | 2015-08-30 | 70.73% | 86412.75
250-06-15 | Construction of Multi-purpose Building- Chess Center Freedom Park | Magugpo Poblacion | 400000 | 2015-06-16 | 2015-09-30 | 78% | 356339.25 |  | On-going
252-06-15 | Concreting of Roads @ Km. 60, New Slaughterhouse | Magdum | 1770443.37 | 2015-07-01 | 2016-03-31 | 77% | 1392893.75 |  | On-going
255-06-15 | Pasalubong Center, Energy Park | Apokon | 3500000 | 2015-05-01 |  | 44.01% | 3158530.25 |  | On- going
258-06-15 | Construction of Parks & Plazas in Barangay & Subdivision @ Purok Cogon, Renzo Village | Visayan Village | 100000 |  |  |  | 64207 |  | For Implementation
259-06-15 | Concreting of Alley @ Prk. Liwanag | M. West | 77000 | 2015-09-17 | 2015-11-17 | 24.47%
260-06-15 | Construction/ Completion of Cultural Communities Education Center @ M. East | Magugpo East | 200000 | 2015-08-01 |  | 63.5% |  |  | On- going
271-07-15 | Construction of One- unit Gazebo | San Agustin | 400000 |  |  |  | 216199.5 |  | For Implementation
272-07-15 | Construction/ Rehab. Of MP Pavement- Concrete Overlay of Existing Basketball Court @ Prk. 1-E, Omila Compound | Apokon | 145000 | 2015-08-16 | 2015-09-30 | 100% | 136377.95 |  | Completed
273-07-15 | Electrification of Bird Park @ Purok Mandapaan | New Balamban | 100000 |  |  |  | 67015 |  | For Implementation
275-07-15 | Construction of Parks & Plazas in Brgy. @ Marquez Triangle Island | Apokon | 150000 | 2015-09-01 | 2015-12-31 | 28.27% | 106585 |  | On-going
258-08-15 | Construction of Parks & Plazas in Brgy. @ Prk. Cogon, Renzo Village | Visayan Village | 100000 | [5 empty] | For Implementation
277-07-15 | Construction of Bleachers @ San Miguel Gym | Brgy. San Miguel | 100000 | 2015-08-16 |  | 94.83% | 83745 |  | On-going
285-07-15 | Completion of Administrative Bldg. @ Purok Mandapaan | New Balamban | 350000 |  |  |  | 242765 |  | For Implementation
303-08-15 | Rehabilitation/Installation of RCPC IGA UY Resettlement | Madaum | 425000 | [5 empty] | POW Approved
304-08-15 | Water Development Program- Construction and Installation of Jetmatic Pump @ Prk. 8 | La Filipina | 60000 | 2015-08-03 | 2015-08-31 | 100% | 56701.22 |  | Completed
305-08-15 | Construction of One- unit Dug Well w/ Iron Removal Filter @ Prk. 13, San Miguel | San Miguel | 63000 |  |  |  | 42680 |  | On- going
308-08-15 | Rehabilitation/Installation of RCPC, Liboganon Resettlement | Liboganon | 135000 |  |  |  | 94012 |  | For Implementation
296-08-15 | Inst. Of 6"diameter Casing Deep Well New Slaughterhouse | Magdum | 1280000 |  |  |  | 1236640 |  | POW Approved
021-01-15 | Installation of Lighting Facilities @ Makabayan, Brgy. San Isidro to Old Brgy. Hall | San Isidro | 300000 |  |  |  | 187707.75 |  | For Implementation
022-01-15 | Installation of Lighting Facilities @ Phoenix Gasoline to Crossing Tuazon High School | Madaum | 300000 |  |  |  | 232391 |  | For Implementation
326-09-15 | Consruction/ Completion of Purok Centers @ Purok 1, La Filipina | La Filipina | 100000 |  |  |  | 75942 |  | For Implementation
001-01-15 | Repair & Maintenance-Road Right of Way | Tagum City | 1040000 |  |  |  | 635600.67 |  | On-going
002-01-15 | Repair & Maintenance-Drainage | Tagum City | 3146379 |  |  |  | 2316775.93 |  | On-going
008-01-15 | Repair & Maintenance-Roads and Road Markings | Tagum City | 3111150 |  |  |  | 1799363.34 |  | On-going
011-01-15 | Repair & Maint.-Electrification, Power & Energy Structures | Tagum City | 5045000 |  |  |  | 4282142.8 |  | On-going
012-01-15 | Repair & Maintenance-Road Right of Way-Clearing Maintenance | Tagum City | 1045000 |  |  |  | 672952.44 |  | On-going
328-09-15 | Construction/ Completion of MPB (Construction of Bincungan E/S Gym) | Bincungan | 1300000 | 2015-10-01 | 2016-01-31 | 35.05% | 887640.57 |  | On- going
330-09-15 | Asphalting of Roads @ Energy Park Compound | Apokon | 800000 | [5 empty] | POW Approved
345-09-15 | Landmark Base Pavement | Apokon | 500000 |  |  |  | 454769 |  | POW Approved
346-09-15 | Painting Materials for Pasalubong Center | Apokon | 500000 |  |  |  | 454769 |  | POW Approved
PROJECTS/PROGRAMS-CONTINUING APPROPRIATION - CURRENT ALLOTED
PROJECTS/PROGRAMS CY 2O14
002-01-14 | Development of San Agustin Eco-Park (Construction of 202m Concrete Pathway, Botanical Park) | San Agustin, Tagum City | 700000 | 2014-01-15 | 2014-09-30 | 100% | 464813 |  | Completed
031-02-14 | Installation of Street lights @ Sator II | Mankilam | 310000 | 2013-02-01 | 2015-01-31 | 100% |  |  | Completed
032-02-14 | Fabrication of Concrete Pole for Lighting Facilities | Tagum City Area | 400000 | 2014-03-03 | 2014-06-15 | 100% | 384666.25 |  | Completed
033-02-14 | Electrification Program-Replacement of Streelights & Rehab of Streetlights lines @ various barangays | Tagum City Area | 1300000 | 2014-05-02 | 2014-09-01 | 100% | 1167936.5 |  | Completed
051-02-14 | Construction pf Purok Centers - Purok Sunflower @ Abad Santos Street | Magugpo Poblacion | 100000 | 2014-10-16 | 2015-02-25 | 100% | 100000 |  | Completed
052-02-14 | Rehabilitation of Asphalted Roads @ various locations (Mercury Drug Service Road, Nat'l. High Way/Caltex Station etc.) | Tagum City Area | 1500000 | 2014-04-01 | 2014-12-20 | 85% | 1409304.33 |  | On-going
061-03-14 | Asphalting of Road-Ashphalt Overlay @ Cacacho Subd. | Mankilam | 500000 | 2014-04-01 | 2014-07-19 | 100% | 470030.98 |  | Completed
062-03-14 | Construction/Completion of Multi-Purpose Bldg (GYM)-La Filipina E/S, | La Filipina | 600000 | 2014-05-16 | 2014-06-30 | 100% | 308462.85 |  | Completed
067-03-14 | Asphalting of Road-Liwayway Service Road | Magugpo East | 900000 | 2014-04-01 | 2014-07-29 | 100% | 869648.97 |  | Completed
069-03-14 | Construction / Completion of Multi-Purpose Building ( RENOVATION OF BARANGAY HALL ) | Madaum | 220000 | 2014-07-02 | 2015-01-15 | 100% | 189224 |  | Completed
073-03-14 | Construction of Purok Centers - Purok 4, Lapu-lapu | Canocotan | 100000 | 2014-07-02 | 2015-01-26 | 100% | 83065 |  | Completed
079-03-14 | Concreting of Road-Prk. Cogon | Visayan Village | 1000000 | 2014-04-01 | 2014-07-31 | 100% | 945488.48 |  | Completed
087-04-14 | Asphalting of Road-Service Road Villa Paraiso-Rhean | Visayan Village | 1000000 | 2014-04-01 | 2014-07-29 | 100% | 960519.54 |  | Completed
088-04-14 | Construction/Completion of Multi-Purpose Bldg., Prk. 3B | San Miguel | 65000 | 2014-09-01 | 2014-09-30 | 100% | 57974 |  | Completed
096-04-14 | Development of San Agustin Eco-Park- Const. of Gazebo Eco-Park | San Agustin | 400000 |  |  | 86.13% | 344513 |  | Completed
116-05-14 | Water Development Program-GAD-Development of Water Facility @ Boy Scout Camp, Energy Park | Apokon | 20000 |  |  |  | 10000 |  | On-going
117-05-14 | Replacement of Submersible Pump 1.5 HP at SP Bldg. | Magugpo Poblacion | 95000 | 2014-12-19 | 2015-02-15 | 100% | 73677.89 |  | Completed
118-05-14 | Repair of 4" dia. Pipe Line at Prk. Bayanihan Brgy Pagsabangan | Pagsabangan | 30000 | 2015-02-02 | 2015-02-28 | 100% | 29485.28 |  | Completed
124-05-14 | Asphalting of Road-Prk. Pioneer | Visayan Village | 1000000 | 2014-06-01 | 2014-08-29 | 100% | 962219.88 |  | Completed
128-05-14 | Development of Energy Park ( CONSTRUCTION OF COMFORT ROOM - Phase 1 ) | Apokon | 1100000 | 2014-06-01 | 2015-05-31 | 100% | 1092391.5 |  | Completed
129-05-14 | Development of Energy Park (Construction of Comfort Room Ph. 2) | Apokon | 160000 | 2014-07-01 | 2014-08-30 | 100% | 142649.26 |  | Completed
136-06-14 | Asphalting of Road-Prk. Tandang Sora Service Road (Letran) | Magugpo West | 750000 | 2014-06-01 | 2014-09-19 | 100% | 721773.05 |  | Completed
137-06-14 | Asphalting of Road-Service Road (Sobrecary-Arriesgado Portion) | Magugpo Poblacion | 1000000 | 2014-06-01 | 2014-08-19 | 95% | 964741.72 |  | On-going
144-06-14 | Construction / Completion of Cultural Communities Education Center @ Prk. Gumamela | Bincungan | 245000 | 2014-09-16 | 2015-02-13 | 100% | 232305.81 |  | Completed
145-06-14 | Construction / Completion of Cultural Communities Education Center @ Prk. Sampaguita | Bincungan | 215000 | 2014-09-16 | 2015-02-13 | 100% | 209253.57 |  | Completed
147-06-14 | Development of Energy Park @ E- Park | Apokon | 590000 | 2014-07-01 | 2014-11-28 | 100% |  |  | Completed
149-06-14 | Fabrication and Installation of Artificial Coral Reefs | Liboganon | 400000 | 2014-09-01 | 2015-11-15 | 100% | 340854 |  | Completed
156-06-14 | Water Development Program - Rehab. Of 1"Ø Pipe Line @ Purok Durian | Pandapan | 170000 | 2014-09-15 | 2015-07-31 | 100% | 124481.5 |  | Completed
157-06-14 | Development of Water Facility at Tagum Public Market | Magugpo East | 385000 | 2014-11-05 | 2015-02-28 | 100% | 346402.15 |  | Completed
163-07-14 | Prk 7, Brgy. La Filipina | La Filipina | 31000 |  |  | 95% |  |  | On-going
165-07-14 | Construction of Purok Center @ Prk. 4-D, Bermudez Plains Subdivision | Apokon | 100000 | 2014-08-18 | 2015-01-26 | 100% | 84583.5 |  | Completed
167-07-14 | Construction of Purok Center @ Prk. Lorenzo Village, Prk. Lorenzo Village | Magugpo East | 100000 | 2014-08-18 | 2015-01-26 | 100% | 83635.5 |  | Completed
168-07-14 | Concreting of Alley @ Prk. Sampaguita | Magugpo West | 50000 | 2014-10-01 | 2015-01-15 | 100% | 45483 |  | Completed
169-07-14 | Concreting of Alley @ Prk. Pag-asa | Magugpo West | 97000 | 2014-09-01 | 2015-01-15 | 100% | 89241 |  | Completed
170-07-14 | Concreting of Alley @ Prk. Kalipay | Magugpo West | 133000 | 2014-10-01 | 2015-01-15 | 100% | 116283 |  | Completed
171-07-14 | Concreting of Alley @ Prk. Sto. Niño, Bagong Lipunan | Magugpo West | 165000 | 2014-08-01 | 2015-01-15 | 100% | 155851.5 |  | Completed
172-07-14 | Concreting of Alley @ Prk. Talisay | Magugpo West | 58000 | 2014-09-01 | 2015-01-15 | 100% | 54225 |  | Completed
175-07-14 | Asphalting of Road-Prk.2 | Nueva Fuerza | 900000 | 2014-08-01 |  | 95.56% | 860071.19 |  | On-going
176-07-14 | Dev't. of Parks & H-ways PROPOSED JOGGING LANE ( Near Immaculada Conception Chapel - Km. 48 ) | Canocotan | 763807 | 2014-08-01 | 2015-03-15 | 100% | 722601 |  | Completed
177-07-14 | Dev't. of Parks & H-ways PROPOSED JOGGING LANE CORNER TIMOG AVENUE - CORNER TIONKO VILLAGE | Canocotan | 1250000 | 2014-08-01 | 2015-06-30 | 100% | 1199021 |  | Completed
183-07-14 | Construction / Completion of Multi-Purpose Gym @ Prk. Orchids, Domingo Village | Magugpo Poblacion | 930000 | 2014-10-01 | 2014-12-31 | 100% | 756772.5 |  | Completed
185-05-14 | Asphalting of Road-Prk.Ferraren Shrineville Subd., Phase II | Magugpo East | 700000 | 2014-09-01 |  | 50% | 667517.95 |  | On-going
195-08-14 | Asphalting of Road-Prk.Bayanihan | Magugpo West | 500000 | 2014-09-01 |  | 60% | 482336.85 |  | On-going
196-08-14 | Asphalting of Road-Golia Avenue | Apokon | 500000 | 2014-09-01 |  | 98% | 472267.84 |  | On-going
202-04-14 | Development of San Agustin Eco-Park, Completion of Gazebo, Eco-park | San Agustin, Tagum City | 100000 | 2014-10-01 | 2015-12-15 | 100% | 80977 |  | Completed
204-08-14 | Development of Magugpo Creek - PROPOSED WALKWAY ( Erlynville Subdivision - Garciaville Subdivision ) | San Miguel | 1000000 | 2014-10-01 | 2015-08-15 | 100% | 838108 |  | Completed
205-08-14 | Development of Magugpo Creek-Proposed Walkway (Prk. Durian-Erlynville Subd.) | San Miguel | 400000 | 2014-10-01 | 2015-03-31 | 100% | 335653 |  | Completed
206-08-14 | Construction / Completion of Multi-Purpose Building ( CONSTRUCTION OF PUROK CENTER ) @ Prk. 9, Malinawon | La Filipina | 220000 | 2014-09-01 | 2015-01-15 | 100% | 197223 |  | Completed
212-09-14 | Construction/Rehab. Of Multi-Purpose Pavement ( GYM ) @ MAKABAYAN SUBDIVISION | San Isidro | 155000 | 2014-10-16 | 2015-02-25 | 100% | 143521.12 |  | Completed
213-09-14 | Water Development Program - Construction and Rehab of Jetmatic Pump. | La Filipina | 35000 | 2015-07-16 | 2015-08-15 | 100% |  |  | Completed
214-09-14 | Construction / Completion of Multi-Purpose Building ( K- 9 Quarter ) @ Energy Park Compound | Apokon | 250000 | 2014-11-01 | 2014-12-31 | 100% | 198311.49 |  | Completed
215-09-14 | Desiltation of Waterways @ Prk. Magkidong | Mankilam | 200000 | 2014-09-01 | 2015-02-15 | 100% | 166400 |  | Completed
217-09-14 | Asphalting of Road-Prk. Sunflower | Magugpo South | 500000 | 2014-11-16 |  | 100% | 467138.89 |  | Completed
218-09-14 | Asphalting of Road-Prk. Sunshine | Visayan Village | 250000 |  |  | 95% | 217744.97 |  | Completed
219-09-14 | Asphalting of Road-Prk. Palmera subd. | Canocotan | 500000 | 2014-11-16 |  | 50% | 476585.5 |  | On-going
224-09-14 | Development of Parks & Highways PROPOSED FISHPOND AND WALL FOUNTAIN @ Home for the Aged, Talisay II | Visayan Village | 80000 | 2015-02-16 | 2015-04-21 | 100% | 75122.85 |  | Completed
225-09-14 | Construction of Bus Stop & Waiting Shed-Tionko Village (Natl Highway) | Canocotan | 80000 | 2014-10-13 | 2015-04-15 | 100% | 71230 |  | Completed
234-10-14 | Concreting of Road ( Additional Lane ) @ Margarita Subdivision | Mankilam | 575000 | 2014-10-01 | 2015-01-15 | 100% | 532472 |  | Completed
239-10-14 | Asphalting of Road-Prk. Pioneer to Magkidong | Mankilam | 1000000 | 2015-01-05 | 2015-12-29 | 40% | 378538.98 |  | On-going
240-10-14 | Concreting of Roads-Prk. Malinawon | La Filipina | 1000000 | 2014-11-01 | 2015-03-31 | 100% | 945911.8 |  | Completed
241-10-14 | Concreting of Road @ Liboganon Road | Liboganon | 1250000 | 2014-11-01 | 2015-04-15 | 100% | 1205606.04 |  | Completed
252-11-14 | Concreting of Road @ Prk. Lanzones | Pandapan | 2100000 | 2015-03-28 | 2015-11-15 | 82% | 1868792.71 |  | On-going
253-11-14 | Concreting of Alley @ Osmeña Extension - Lay Formation Center | Magugpo West | 420000 | 2014-12-01 | 2015-03-15 | 100% | 419028 |  | On-going
254-11-14 | Development of Bird Park-Concreting of Pathways | New Balamban | 275000 |  |  |  | 128583 |  | On-going
255-11-14 | Development of Bird Park-Concreting of Pathway, Prk. Mandapaan | New Balamban | 125000 | 2014-11-12 |  | 55.15% | 95643.5 |  | On-going
273-12-14 | Asphalting of Road-Prk. Durian | Magugpo North | 441600 |  |  |  | 323684.34 |  | For Implementation
PROJECTS/PROGRAMS-CONTINUING APPROPRIATION - CURRENT UNALLOTED
PROJECTS/PROGRAMS CY 2O14
| Development of Resettlement Areas | Tagum City | 1000000
| Fencing of Relocation Sites | Tagum City | 1000000
Desiltation of waterways
| Construction/Completion of Cultural Communities Education | Tagum City | 300000
| Construction/Completion of Parks & Plaza in Brgys & Subdivisions | Tagum City | 250000
| Fabrication & Installation of Artificial Coral Reef | Liboganon | 200000 | 2015-05-28 | 2015-10-15 | 50% |  |  | On- going
PROJECTS/PROGRAMS-CONTINUING APPROPRIATION - CURRENT UNALLOTED
PROJECTS/PROGRAMS CY 2O13
016-01-13 | Asphalting of Road-Asphalt Overlay @ Brgy. La Filipina - Brgy. San Agustin Road Section | La Filipina | 1000000 | 2013-01-02 | 2014-12-31 | 10% | 965666.53 |  | Suspended
017-01-13 | Asphalting of Road-Asphalt Overlay @ Service Road (Iglesia ni Cristo Portion) | Magugpo East | 500000 | 2013-01-02 | 2014-05-20 | 100% | 490995.07 |  | For Implementation
022-01-13 | Asphalting of Road-Asphalt Overlay @ North Eagle I | Visayan Village | 500000 | 2013-03-01 | 2014-12-31 | 100% | 494779.38 |  | Completed
030-01-13 | Asphalting of Road-Asphalt Overlay @ Prk.29 | Madaum | 500000 | 2013-03-01 | 2015-05-04 | 100% | 493529.36 |  | Completed
030-01-13 | Asphalting of Roads- Prk. 29 | Brgy. Madaum | 500000 | 2013-03-01 |  | 100% |  |  | Completed
054-01-13 | Concreting of Road-Domingo Village | Magugpo Poblacion | 500000 | 2013-09-01 | 2014-12-31 | 100% | 489449.23 |  | Completed
070-02-13 | Install. Of Streetlights @ Sator II | Mankilam | 310000 | 2013-02-01 | 2015-01-31 | 100% | 289892.73 |  | Completed
169-07-13 | Development of Bird Park Phase III-Mandapaan | New Balamban | 350000 | 2013-09-01 | 2014-01-15 | 100% | 321817 |  | Completed
178-09-13 | Development of Magugpo Creek-along Sobrecary to Bonifacio St (Landscaping) | Magugpo South | 340000 | 2013-10-01 | 2014-06-15 | 100% | 275981 |  | Completed
196-09-13 | Development of Energy Park (Water System) | Apokon | 100000 | 2013-10-07 | 2013-12-31 | 100% | 91901.53 |  | Completed
197-09-13 | Development of Magugpo Creek-Punzalan Avenue (Electrical) | Magugpo South | 260000 | 2013-01-16 | 2014-03-31 | 100% | 172995 |  | Completed
198-09-13 | Development of Energy Park (Bird Cage) | Apokon | 150000 | 2013-10-01 | 2014-05-31 | 100% | 125760 |  | Physically Completed
249-06-15 | Construction/ Completion of Multi- purpose Bldg.. ( Purok Center) @ Prk. 5-A | La Filipina | 100000 | 2015-07-15 | 2015-08-30 | 70.73% | 86412.75 |  | On- going
250-06-15 | Construction of Multi-purpose Building- Chess Center Freedom Park | Magugpo Poblacion | 400000 | 2015-06-16 | 2015-09-30 | 78% | 356339.25 |  | On-going
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
Prepared by: |  |  |  |  | Attested by:
| NORHANIAH S. DISOMA, CPA |  |  |  |  | RODILIO S. DINOPOL, CE
| Clerk I |  |  |  |  | Project Monitoring In- Charge
Noted by: |  |  |  |  | Approved by:
| ARCADIA E. YLANAN, CPA, MBA |  |  |  |  | ALLAN L. RELLON, DPA, Ph.D.
| City Budget Officer |  |  |  |  | City Mayor

## SEF
FDP Form 7 - Special Education Fund Fund
Republic of the Philippines
Province of Davao del Norte
City of Tagum
OFFICE OF THE CITY BUDGET OFFICER
PROJECT MONITORING REPORT
SPECIAL EDUCATION FUND
For the 3rd Quarter, CY 2015
Province, City or Municipality: TAGUM CITY
Ref No. | Particulars | Location | Total Cost | Date Started | Target Completion Date | % of Completion | Total Cost Incurred to Date | No. of Extensions, if any | Remarks
308-08-15 | Fabrication of Various School Furnitures @ Motorpool Tipaz | Magugpo East | 500000 |  |  |  | 496757 |  | COMPLETED
062-03-15 | Development of School Facilities- Horizontal Stainless Water Tank @ Laureta National High School | San Miguel | 525000 | 2015-03-23 | 2015-06-15 | 100% |  |  | Completed as per POW
007-01-15 | Repair & Maintenance of School Facilities | Various Schools | 2593460 |  |  |  | 2269411.23
009-01-15 | Repair & Maintenance of School Lighting Facilities | Various Schools | 1149956 |  |  |  | 683918.5
015-01-15 | Construction/ Rehab. & Upgrading of Electrical Power Lines @ Public Schools of Tagum City | Public Schools of Tagum City | 1000000 |  |  |  | 858835 |  | POW Approved
062-03-15 | Repair & Maintenance of School Facilities Horizontal Stainless Water Tank @ Laureta Nat'l HS | San Miguel | 480250.6 |  |  |  | 480250.6
063-03-15 | Repair & Maintenance of School Facilities Horizontal Stainless Water Tank @ Jose Tuason Nat'l H/S | Madaum | 502524.31 |  |  |  | 502524.31
064-03-15 | Development of School Facilities- Horizontal Stainless Water Tank @ Rizal Elem. School | Magugpo South | 525000 | 2015-04-29 | 2015-07-06 | 100% |  |  | Completed as per POW
065-03-15 | Billeting Venue at Tagum City National Comprehensive H/S | La Filipina | 76965 |  |  |  | 76965 |  | Completed as per POW
066-03-15 | Billeting Venue at La Filipina National H/S | La Filipina | 93426 |  |  |  | 93426 |  | Completed as per POW
067-03-15 | Billeting Venue at Jose Tuazon, Jr. Memorial National H/S | Madaum | 105663 |  |  |  | 105663
068-03-15 | Billeting Venue at Madaum Elementary School | Madaum | 69152 |  |  |  | 69152
069-03-15 | Billeting Venue at Visayan Central Elementary School | Visayan Village | 77485 |  |  |  | 77485
070-03-15 | Billeting Venue at Apokon Elementary School | Apokon | 61335 |  |  |  | 61335
071-03-15 | Billeting Venue at Laureta National High School | Laureta | 52075 |  |  |  | 52075
072-03-15 | Billeting Venue at Union Elementary School | Mankilam | 48075 |  |  |  | 48075
073-03-15 | Billeting Venue at Laureta Elementary School | San Miguel | 98173 |  |  |  | 98173
074-03-15 | Billeting Venue at Mankilam Elementary School | Mankilam | 78300 |  |  |  | 78300
075-03-15 | Billeting Venue at MPCES | Magugpo South | 104187 |  |  |  | 104187
076-03-15 | Billeting Venue at La Filipina Elementary School | La Filipina | 113095 |  |  |  | 113095
077-03-15 | Billeting Venue at Don Ricardo Briz Elementary School | Magugpo East | 99050 |  |  |  | 99050
078-03-15 | Billeting Venue at MPIES | Magugpo South | 67357 |  |  |  | 67357
079-03-15 | Billeting Venue at Tagum City National Highschool | Visayan Village | 96101 |  |  |  | 96101
080-03-15 | Billeting Venue at Mangga E/S | Visayan Village | 59895 |  |  |  | 59895
081-03-15 | Billeting Venue at Rizal Elementary School | Magugpo South | 81278 |  |  |  | 81278
082-03-15 | Billeting Venue at Tagum City National Trade School | Apokon | 107215 |  |  |  | 107215
115-03-15 | Development of School Facilities- Horizontal Stainless Water Tank @ Mangga E/S | Visayan Village | 525000 | 2015-04-08 | 2015-07-31 | 100% |  |  | Completed as per POW
116-03-15 | Repair & Maintenance of School Facilities Horizontal Stainless Water Tank @ Tagum City Nat'l Comp. H/S | Mankilam | 238119 |  |  |  | 238119
117-03-15 | Repair & Maintenance of School Facilities Horizontal Stainless Water Tank @ Madaum Elementary School | Madaum | 213357 |  |  |  | 213357
118-03-15 | Repair & Maintenance of School Facilities Horizontal Stainless Water Tank @ Tagum City Nat'l Highschool | Visayan Village | 249120.5 |  |  |  | 249120.5
115-03-15 | Repair & Maintenance of School Facilities Horizontal Stainless Water Tank @ Mangga Elementary School | Visayan Village | 480000 |  |  |  | 455003.75
119-03-15 | Water Development Program (Dev't of School Facilities) @ Magugpo Pilot Imelda Elem. School | Magugpo South | 525000 | 2015-05-12 | 2015-07-17 | 100% |  |  | Completed as per POW
121-03-15 | Development of School Facilities _ Horizontal Stainless Water Tank @ Jose Tuason National Hish School | Madaum | 525000 | 2015-03-23 | 2015-06-15 | 100% |  |  | Completed as per POW
122-03-15 | Development of School Facilities- Horizontal Stainless Water Tank @ La Filipina Elem. School | La Filipina | 325000 | 2015-04-30 | 2015-07-06 | 100% | 310347.96 |  | Completed as per POW
123-03-15 | Development of School Facilities- Horizontal Stainless Water Tank @ La Filipina NHS | La Filipina | 470000 | 2015-05-14 | 2015-07-31 | 100% | 454454.19 |  | Completed as per POW
190-04-15 | Repair Maintenance of School Building @ Madaum Elem. School | Madaum | 250000 | 2015-05-22 | 2015-07-15 | 44.43%
201-04-15 | Repair Maintenance of School Building @ La Filipina Elem. School | La Filipina | 250000 | 2015-04-16 | 2015-05-15 | 100%
205-04-15 | Repair Maintenance of School Building @ La Filipina National Highschool | La Filipina | 250000 | 2015-04-16 | 05/15/145 | 99.37%
028-02-14 | School Fencing @ Bincungan Elem. School | Bincungan | 170000 | 2014-02-17 | 2015-01-15 | 100% |  |  | Completed
029-02-14 | School Fencing @ Madaum Elem. School | Madaum | 330000 | 2010-02-17 | 2015-01-15 | 100% |  |  | Completed
078-03-14 | Construction/ Completion of School Building ( Conventional Type ) Busaon E/S, Brgy. Busaon | Busaon | 171279 |  |  |  | 137760
092-03-15 | Construction of Temporary Shower Rooms @ Apokon Elem. School | Apokon | 136703 |  |  |  | 136703
093-03-15 | Construction of Temporary Shower Rooms @ Rizal Elementary School | Magugpo South | 100618 |  |  |  | 100618
094-03-15 | Construction of Temporary Shower Rooms @ Tagum City National High School | Visayan Village | 136691.2 |  |  |  | 136691.2
095-03-15 | Construction of Temporary Shower Rooms @ Tagum City Nat'l Comprehensive H/S | Mankilam | 137971 |  |  |  | 137971
096-03-15 | Construction of Temporary Shower Rooms @ MPIES | Magugpo South | 137001 |  |  |  | 137001
097-03-15 | Construction of Temporary Shower Rooms @ Tagum City Nat'l Trade School | Apokon | 114853.2 |  |  |  | 114853.2
098-03-15 | Construction of Temporary Shower Rooms @ MPCES | Magugpo South | 123077 |  |  |  | 123077
099-03-15 | Construction of Temporary Shower Rooms @ Visayan Village Central Elementary School | Visayan Village | 125846.16 |  |  |  | 125846.16
100-03-15 | Construction of Temporary Shower Rooms @ Madaum Elementary School | Madaum | 117116.2 |  |  |  | 117116.2
101-03-15 | Construction of Temporary Shower Rooms @ Don Ricardo Briz E/S | Magugpo East | 116093 |  |  |  | 116093
102-03-15 | Construction of Temporary Shower Rooms @ La Filipina Na'l Highschool | La Filipina | 121871 |  |  |  | 121871
103-03-15 | Construction of Temporary Shower Rooms @ Laureta Elementary School | San Miguel | 120595 |  |  |  | 120595
104-03-15 | Construction of Temporary Shower Rooms @ Mangga Elementary School | Visayan Village | 115060.2 |  |  |  | 115060.2
105-03-15 | Construction of Temporary Kitchen @ Jose Tuason Jr., Memorial H/S | Madaum | 105114 |  |  |  | 105114
106-03-15 | Construction of Temporary Shower Rooms @ MPIES | Magugpo South | 107554 |  |  |  | 107554
107-03-15 | Construction of Temporary Shower Rooms @ Tagum Nat'l Comprehensive H/S | Mankilam | 148369.99 |  |  |  | 148369.99
108-03-15 | Construction of Temporary Shower Rooms @ Rizal Elementary School | Magugpo South | 116222.99 |  |  |  | 116222.99
109-03-15 | Construction of Temporary Shower Rooms @ La Filipina Na'l Highschool | La Filipina | 147448.99 |  |  |  | 147448.99
110-03-15 | Construction of Temporary Shower Rooms @ MPCES | Magugpo South | 129960.31 |  |  |  | 129960.31
111-03-15 | Construction of Temporary Shower Rooms @ Laureta Nat'l Highschool | San Miguel | 133997.57 |  |  |  | 133997.57
112-03-15 | Construction of Temporary Shower Rooms @ Don Ricardo Briz E/S | Magugpo East | 147803.99 |  |  |  | 147803.99
113-03-15 | Construction of Temporary Shower Rooms @ Tagum City Nat'l H/S | Visayan Village | 148092 |  |  |  | 148092
114-03-15 | Construction of Temporary Shower Rooms @ Mangga Elementary School | Visayan Village | 148137.99 |  |  |  | 148137.99
119-03-15 | Dev't of School Facilities @ MPIES (Sped) Water System | Magugpo South | 318000 |  |  |  | 303374.43
317-09-15 | Boyscout Mess Hall @ E-park, Apokon Road | Apokon | 175000 | 2015-10-01 | 2015-10-31 | 67.08%
319-09-15 | Repair and Maintenance of Temporary Toilet (Boyscout) @ Energy Park | Apokon | 950000 | 2015-10-01 | 2015-10-31 | 66.7%
320-09-15 | Boyscout Meeting Hall @ Energy Park | Apokon | 105000 | 2015-10-01 | 2015-10-31 | 75%
332-09-15 | Construction of School Building/ Classroom @ Tagum Nat'l Trade School | Apokon | 9600000.01 |  |  |  | 6510859
333-09-15 | Construction of School Building/ Classroom @ Apokon E/S | Apokon | 6500000 |  |  |  | 4109434
334-09-15 | Construction of School Building/ Classroom @ Mankilam E/S | Mankilam | 5600000.01 |  |  |  | 3705264
335-09-15 | Construction of School Building/ Classroom @ Rizal Elem. School | Magugpo South | 6850000.01 |  |  |  | 4552774
336-09-15 | Construction of School Building/ Classroom @ MPCES | Magugpo South | 8600000.01 |  |  |  | 5556931
337-09-15 | Construction of School Building/ Classroom @ Tagum City Comprehensive H/S (Pandapan Extension) | Pandapan | 3900000.01 |  |  |  | 2598999.5
338-09-15 | Construction of School Building/ Classroom @ La Filipina E/S | La Filipina | 3850000 |  |  |  | 2550060
339-09-15 | Construction of School Building/ Classroom @ Union Elem. School | Mankilam | 4300000 |  |  |  | 2785736
340-09-15 | Construction of School Building/ Classroom @ Visayan Central Elem. School | Visayan Village | 5300000 |  |  |  | 3449107
341-09-15 | Construction of School Building/ Classroom @ Mangga Elementary School | Visayan Village | 4910000 |  |  |  | 1609867
342-09-15 | Construction of School Building/ Classroom @ Liboganon Elem. School | Liboganon | 1600000 |  |  |  | 1112233
343-09-15 | Construction of School Building/ Classroom @ Tagum Nat'l Comprehensive Highschool | Mankilam | 1140000 |  |  |  | 793510
344-09-15 | Construction of School Building/ Classroom @ Pipisan Maug Nat'l Highschool | Bincungan | 1250000 |  |  |  | 870113
154-06-14 | Rehabilitation/ Construction of Drainage (w/o cover) @ Wakan Relocation Site | San Isidro | 826576 | 2014-09-01 | 2015-03-15 | 100% |  |  | Completed as per POW
155-06-14 | Construction/ Completion of School Building @ Rizal E/S | M. South | 102147.34 | 2015-02-02 |  | 90% |  |  | On- going
179-07-14 | Construction of School Building @ Magugpo Pilot Central E/S ( 5 Makeshift Classroom) | M. South | 1730000 | 2014-08-16 | 2015-02-28 | 100% |  |  | Completed as per POW
223-09-14 | Fencing of Schools @ San Agustin E/S | San Agustin | 600000 | 2014-10-01 | 2015-02-28 | 100% |  |  | Completed
243-10-14 | Drainage Improvement (Construction of Slope Protection) Timog Road | Visayan Village | 919461.75 | 2014-11-16 | 2015-04-30 | 100% |  |  | Completed as per POW
260-11-14 | Construction of Classroom ( Senior High School Program ) @ TCNHS (Pandapan Campus) | Pandapan | 1000000 | 2014-12-01 | 2015-07-31 | 100% |  |  | Completed as per POW
267-11-14 | Construction of School Classroom Senior High School Program ( Phase 1) | Bincungan | 1000000 | 2015-01-01 | 2015-07-31 | 100% |  |  | Completed as per POW
268-11-14 | Concreting of Road @ Prk. 1- Prk. 2 | Liboganon | 3552480.14 | 2015-01-05 | 2014-07-31 | 100% |  |  | Completed
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
Prepared by: |  |  |  | Attested by:
| NORHANIAH S. DISOMA, CPA |  |  |  | RODILIO S. DINOPOL, CE
| Clerk I |  |  |  | Project Monitoring In- Charge
Noted by: |  |  |  | Approved by:
| ARCADIA E. YLANAN, CPA, MBA |  |  |  | ALLAN L. RELLON, DPA, Ph.D.
| City Budget Officer |  |  |  | City Mayor

## COMPLETED (Trust Fund)
FDP Form 7 - Trust Fund
Republic of the Philippines
Province of Davao del Norte
City of Tagum
OFFICE OF THE CITY BUDGET OFFICER
PROJECT MONITORING REPORT
For the 3rd Quarter, CY 2015
Province, City or Municipality: TAGUM CITY
Ref No. | Particulars | Location | Total Cost | Date Started | Target Completion Date | % of Completion | Total Cost Incurred to Date | No. of Extensions, if any | Remarks
149-03-15 | Concreting of Road Iga Uy Resettlement | Madaum | 1205689.2 | [5 empty] | Completed
154-03-15 | Construction/ Completion of School Building National Child Development Center | M. Poblacion | 21000 | 2015-06-16 | 2015-07-31 | 100% | 19125 |  | Completed
190-04-15 | Repair & Maintenance of School Building @ Madaum Elem. School | Madaum | 250000 | 2015-05-22 | 2015-08-31 | 100% | 239884.95 |  | Completed
191-04-15 | Repair & Maintenance of School Building @ Laureta Elem. School | San Miguel | 250000 | 2015-04-18 | 2015-08-11 | 100% | 233540 |  | Completed
192-04-15 | Repair & Maintenance of School Building @ Visayan Village Elem. School | Visayan Village | 250000 | 2015-04-18 | 2015-08-31 | 100% | 233232 |  | Completed
193-04-15 | Repair & Maintenance of School Building @ Magugpo Pilot Imelda E/S | M. South | 250000 | 2015-04-16 | 2015-09-15 | 100% | 239973 |  | Completed
194-04-15 | Repair & Maintenance of School Building @ Jose Tuason Memorial High School | Madaum | 250000 | 2015-04-25 | 2015-08-31 | 100% | 211610 |  | Completed
195-04-15 | Repair & Maintenance of School Building @ Laureta National H/S | San Miguel | 250000 | 2015-04-18 | 2015-08-11 | 100% | 243531.94 |  | Completed
196-04-15 | Repair & Maintenance of School Building @ Apokon E/S | Apokon | 250000 | 2015-04-20 | 2015-07-31 | 100% | 242441 |  | Completed
197-04-15 | Repair & Maintenance of School Building @ Mankilam Elem School | Mankilam | 250000 | 2015-04-18 | 2015-07-06 | 100% | 213884 |  | Completed
198-04-15 | Repair & Maintenance of School Building @ Magugpo Central Elem. School | M. South | 250000 | 2015-04-20 | 2015-08-31 | 100% | 232480 |  | Completed
200-04-15 | Repair & Maintenance of School Building @ Union Elem. School | Mankilam | 250000 | 2015-04-18 | 2015-08-31 | 100% | 214716 |  | Completed
201-04-15 | Repair & Maintenance of School Building @ La Filipina Elem. School | La Filipina | 250000 | 2015-04-16 | 2015-09-22 | 100% | 239469 |  | Completed
203-04-15 | Repair & Maintenance of School Building @ Don Ricardo Briz Elem. School | M. East | 250000 | 2015-04-18 | 2015-06-15 | 100% | 238819 |  | Completed
204-04-15 | Repair & Maintenance of School Building @ Mangga Elem. School | Visayan Village | 250000 | 2015-04-16 | 2015-08-31 | 100% | 235219 |  | Completed
205-04-15 | Repair & Maintenance of School Building @ La Filipina National H/S | La Filipina | 250000 | 2015-04-16 | 2015-07-31 | 100% | 220659.3 |  | Completed
206-04-15 | Repair & Maintenance of School Building @ Tagum National Trade School | Apokon | 250000 | 2015-04-20 | 2015-08-31 | 100% | 239056.5 |  | Completed
207-04-15 | Repair & Maintenance of School Building @ Tagum City National H/S | Visayan Village | 250000 | 2015-04-16 | 2015-08-31 | 100% | 231651 |  | Completed
001-01-14 | DepEd- Development of School Furnitures 2014 | Various Schools | 1000000 | 2014-01-06 | 2015-08-05 | 100% | 943915.5 |  | Completed
059-03-14 | Fabrication of School Furniture 2014 B | Various Schools | 900000 | 2014-03-04 | 2015-04-07 | 100% | 893926 |  | Completed
148-06-14 | Fabrication of School Furniture 2014 A | Various Schools | 1000000 | 2014-06-23 | 2015-08-11 | 100% | 999922.5 |  | Completed
149-03-15 | Concreting of Road Iga Uy Resettlement | Madaum | 1205689.2 | 2015-08-01 | 2015-03-15 | 100% |  |  | Completed
154-06-14 | Rehabilitation/ Construction of Drainage @ Wakan Relocation Site | Brgy. San Isidro | 826576 | 2014-09-01 | 2015-03-15 | 100% | 805670 |  | Completed
235-10-14 | CDRRMO- Other Rescue and Response Equipment Construction of Trillon Tower |  | 450000 | 2014-11-10 | 2015-04-15 | 100% | 415372.72 |  | Completed
242-10-14 | Tagum City Local Road Funds CY 2013, San Miguel Road | San Miguel | 695223.91 | 2014-11-10 |  | 100% | 595132.28 |  | Completed
243-10-14 | Tagum City Local Road Funds CY 2013, Timog Road | Visayan Village | 919461.75 | 2014-11-16 | 2015-04-30 | 100% | 891667.92 |  | Completed
244-10-14 | Tagum City Local Road Funds CY 2013, Villa Paraiso | Visayan Village | 1444455.34 |  |  | 100% | 1433658.73 |  | Completed
268-11-14 | DA- DIDP, Concreting of Prk. 2 Brgy. Liboganon | Liboganon | 3552480.14 | 2015-01-05 | 2015-07-31 | 100% | 2778101.96 |  | Completed
010-01-13 | Asphalting of Laureta School Road towards Resettlement Road. Section | Laureta | 970000 | 2013-07-30 | 2014-09-24 | 100% | 958122.58 |  | Completed
011-01-13 | Asphalting of Bincungan Interior Road System | Bincungan | 970000 | 2013-08-01 | 2014-09-24 | 100% | 29289.9 |  | Completed
012-01-13 | Asphalting of RTU Resettlement (Continuation) RD. Secc. |  | 1484100 | 2013-08-15 | 2014-09-24 | 100% | 1478715.1 |  | Completed
154-05-13 | Concreting of Road at Visayan Village towards Jalandoni Subdivision | Visayan Village | 1120000 | 2013-08-05 | 2014-09-24 | 100% | 949837 |  | Completed
155-05-13 | Concreting of Road Iga Uy Resettlement Road Sect. | Madaum | 1120000 | 2013-08-05 | 2014-01-07 | 100% | 937510.98 |  | Completed
172-08-13 | DA BFAR- Proposed Construction of Multi Species Algal Tank, Plumbing & Electrical | Liboganon | 499800 | 2013-11-12 | 2015-10-01 | 100% | 485330.11 |  | Completed
173-08-13 | Proposed Construction of Saline Tilapia Hatchery | Brgy. Bincungan | 190640 | 2013-11-21 | 2015-10-01 | 100% | 165129.81 |  | Completed
175-08-13 | Proposed Construction of Multi Species (Larval Building) | Liboganon | 1635800 | 2013-11-12 | 2015-09-08 | 100% | 11598582.75 |  | Completed
174-08-13 | PROPOSED Construction of Multi Species (Reservoir/ Water Tank) | Liboganon | 223760 | 2013-11-12 | 2015-09-15 | 100% | 211493 |  | Completed
180-09-13 | Construction of Drainage Rehabilitation and CHB Lining of Drainage (w/o cover) @ Mankilam Creek (Tadena) | Mankilam | 1500000 | 2013-09-17 | 2014-08-13 | 100% | 1487304.82 |  | Completed
181-09-13 | Construction of Drainage Rehabilitation and CHB Lining of Drainage (w/o cover) @ San Miguel Creek (Fajardo) | San Miguel | 1000000 | 2013-09-17 | 2014-05-30 | 100% | 992606.5 |  | Completed
AD-300-14-008 | DENR- National Greening Program | Tagum City | 37500 |  |  | 100% | 37500 |  | Completed
AD-30014-040 | DENR- National Greening Program | Tagum City | 93750 |  |  | 100% | 93750 |  | Completed
AD-300-14-064 | DENR- National Greening Program | Tagum City | 93750 |  |  | 100% | 93750 |  | Completed
AD-300-14-017 | Operation Hugpong na Serbisyo | Tagum City | 50000 |  |  |  | 38641 |  | Completed
AD-300-14-026 | Hugpong Serbisyo para sa Tagumenyos Post Activity Assessment, Feedbacking and Evaluation | Tagum City | 160000 |  |  |  | 148232 |  | Completed
AD-300-14-034 | For the Meals of Volunteers and Manpower of Hugpong na Sebisyon para sa Tagumenyos | Tagum City | 50000 |  |  | 100% | 46869 |  | Completed
AD-300-15-013 | Musikahan Festival 2015 | Tagum City | 177500 |  |  | 100% | 176971 |  | Completed
AD-300-15-015 | Musikahan Festival 2015 | Tagum City | 190000 |  |  | 100% | - |  | Completed
AD-300-14-12 | Musikahan Festival 2015 | Tagum City | 143000 |  |  | 100% | 138400 |  | Completed
AD-300-14-009 | Musikahan Festival 2015 | Tagum City | 215500 |  |  | 100% | 211000 |  | Completed
AD-300-14-016 | Musikahan Festival 2015 | Tagum City | 150000 |  |  | 100% | 144700 |  | Completed
AD-300-14-042 | Musikahan Festival 2015- PAGCOR | Tagum City | 49229.2 |  |  | 100% | 43299.2 |  | Completed
AD-300-14-043 | 1st Mutya ng Tagum 2013- PAGCOR | Tagum City | 99314 |  |  | 100% | 57158.95 |  | Completed
AD-300-14-046 | Barangay Musikahan | Tagum City | 10000 |  |  | 100% | 8075 |  | Completed
AD-300-14-047 | Pre Kadagayaan Whole year campaign |  | 10514 |  |  | 100% | 10514 |  | Completed
AD-300-14-029 | Participation to Kadagayaan Festival |  | 50000 |  |  | 100% | 49680 |  | Completed
AD-300-14-032 | Participation to Kadagayaan Festival 2 |  | 50000 |  |  | 100% | 49200 |  | Completed
AD-300-14-035 | Kadagayaan Festival Post Evaluation & 2015 Planning |  | 31160 |  |  | 100% | 30659.66 |  | Completed
439-007-0013 | Fiesta Trade Fair | Tagum City | 77200 |  |  | 100% | 76710 |  | Completed
AD-300-14-028 | Donation for Fun Run of Peace | Tagum City | 28950 |  |  | 100% | - |  | Completed
AD-300-14-065 | Literacy Coordinating Council- Cash Award (Social Services) | Tagum City | 54000 |  |  |  | - |  | Completed
AD-300-14-071 | Literacy Coordinating Council- Cash Award (Various Literacy Programs & Projects) | Tagum City | 146000 |  |  |  | 134726.52 |  | Completed
AD-300-14-083 | CMO- Business License Section- Businesss for Licensing and Inspection Fee | Tagum City | 65120 |  |  |  | 64200 |  | Completed
AD-300-15-011 | CMO- Business License Section- Businesss for Licensing and Inspection Fee | Tagum City | 180000 |  |  |  | 166218 |  | Completed
AD-300-14-069 | DILG- Galing Pook Award Night Market | Tagum City | 35000 |  |  |  | 25343 |  | Completed
AD-300-14-082 | DILG- Galing Pook Award Night Market | Tagum City | 50480 |  |  | 100% | 50480 |  | Completed
AD LABOR-14-007 | Saint Peter Green Program | Tagum City | 872310 |  |  | 100% | 844476.17 |  | Completed
AD LABOR-14-013 | Saint Peter Green Program | Tagum City | 472250 |  |  | 100% | 457215 |  | Completed
AD LABOR-14-044 | Saint Peter Green Program | Tagum City | 472250 |  |  | 100% | 275220 |  | Completed
AD LABOR-15-003 | Saint Peter Green Program | Tagum City | 472250 |  |  | 100% | 322452 |  | Completed
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
Prepared by: |  |  |  | Attested by:
| NORHANIAH S. DISOMA, CPA |  |  |  | RODILIO S. DINOPOL, CE
| Clerk I |  |  |  | Project Monitoring In- Charge
Noted by: |  |  |  | Approved by:
| ARCADIA E. YLANAN, CPA, MBA |  |  |  | ALLAN L. RELLON, DPA, Ph.D.
| City Budget Officer |  |  |  | City Mayor

## INCOMPLETE PROJ.(TrustFund)
FDP Form 7 - Trust Fund
Republic of the Philippines
Province of Davao del Norte
City of Tagum
OFFICE OF THE CITY BUDGET OFFICER
PROJECT MONITORING REPORT
TRUST FUND
For the 3rd Quarter, CY 2015
Province, City or Municipality: TAGUM CITY
Ref No. | Particulars | Location | Total Cost | Date Started | Target Completion Date | % of Completion | Total Cost Incurred to Date | No. of Extensions, if any | Remarks
053-02-15 | DSWD- Core Shelter Assistance Program |  | 2000000 | 2015-05-28 |  | 95% | 1697973.5 |  | On-going
199-04-15 | Repair & Maintenance of School Building @ Tagum City National Comprehensive H/S | Mankilam | 250000 | 2015-04-18 |  |  | 235279.3 |  | On-going
202-04-15 | Repair & Maintenance of School Building @ Rizal Elem. School | M. South | 250000 | 2015-04-18 |  | 97% | 226397.5 |  | On-going
246-06-15 | Construction of Rice Mill Housing |  | 250000 | 2015-06-11 |  |  | 160574
256-06-15 | Concreting of Roads @ Prk. Mauswagon | M. South | 538000 | [5 empty] | POW Approved
298-08-15 | Concreting of Roads @ Prk. Alvarida | Pagsabangan | 2000000 | 2015-08-13 |  |  | 609330.62 |  | For Implementation
299-08-15 | Concreting of Roads @ Sitio Kasilak | San Agustin | 2000000 | 2015-08-13 |  |  | 1137898 |  | On-going
300-08-15 | Concreting of Roads @ Prk. Alambre | San Isidro | 2000000 | 2015-08-13 |  |  | 1039509 |  | On-going
301-08-15 | Concreting of Roads @ Brgy. San Isidro- Brgy. Canocotan (Tano Area) Road | San Isidro | 2000000 | 2015-08-13 | 2015-12-15 | 15% | 1149255.5 |  | On-going
322-09-15 | Construction/ Completion of Multi-purpose Building, Pasalubong Center | Apokon | 3000000 | 2015-09-14 | 2015-11-15 | 30% | 2697234.2
090-04-14 | NMIS- Construction of Tagum City's New "AA" Slaughter House | Madaum | 10000000 | 2014-05-01 | 2015-05-31 | 98.71% | 9348730.57 |  | On-going
244-10-14 | Tagum City Local Road Funds CY 2013, Villa Paraiso | Visayan Village | 1444455.34 |  |  |  | 1433658.73
276-12-14 | Tagum City Local Road Funds CY 2013, Pioneer Avenue | Brgy. Poblacion | 2873219.52 |  |  |  | 2340874.1
148-04-13 | DepEd- Fabrication of School Furniture | Tagum City | 1722037.4 |  |  |  | -
322-09-15 | Const./Completion of Multi-Purpose Bldg., PASALUBONG CENTER | Apokon | 3000000 | 2015-09-14 | 2015-10-31 | 67% | 2697234.2 |  | On-going
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
Prepared by: |  |  |  | Attested by:
| NORHANIAH S. DISOMA, CPA |  |  |  | RODILIO S. DINOPOL, CE
| Clerk I |  |  |  | Project Monitoring In- Charge
Noted by: |  |  |  | Approved by:
| ARCADIA E. YLANAN, CPA, MBA |  |  |  | ALLAN L. RELLON, DPA, Ph.D.
| City Budget Officer |  |  |  | City Mayor